## README
SPR Techforge — Testing Workbook
How to use this workbook
• User Stories — 140+ pre-loaded stories with detailed acceptance criteria. Update Status, Owner, Sprint as you go.
• Test Cases — Manual test cases linked back to stories. Add more rows as you write new ones.
• Bugs — Single sheet for ALL bug data (was bug-report + bug-tracker). Status, Severity, Priority columns have dropdowns.
• Test Execution — Pass/Fail/Blocked log per cycle. Create one row per (test case × cycle) — never overwrite.
• Sprint Board — 6-sprint plan with tester assignments. Adjust dates and owners as needed.
• Automation Coverage — Track which manual cases also have automated Playwright tests.
Status values (use the dropdowns; don't type freely)
Stories : Backlog · Sprint · In Design · In Test · Blocked · Failed · Done
Tests : Active · Draft · Archived
Bugs : New · Open · In Progress · Fixed · Verified · Closed · Reopened · Deferred · Won't Fix
Exec : Pass · Fail · Blocked · Not Run · Skipped · Deferred
Priority: P0 (showstopper) · P1 · P2 · P3 (cosmetic)
Severity: Critical · High · Medium · Low
Conventions
• Story IDs are SPR-### · Test case IDs are TC-### · Bug IDs are BUG-###.
• One bug per row. If a flow has three issues, file three bugs.
• Don't move a bug to Verified without actually rerunning the failing scenario.
• Once you save this workbook with your own edits, save it to your shared drive — the copy in the repo is a fresh template.
Need to reset the workbook to its scaffolded state?
cd testing/generator && npm install && npm run build
Reference docs (read these alongside the workbook):
testing/01-scope.md — what we test, environments, browsers
testing/02-test-plan.md — strategy, roles, schedule, criteria
testing/03-automation-plan.md — Playwright pyramid, phased rollout
testing/04-agile-process.md — sprints, ceremonies, DoR/DoD, lifecycles

## User Stories
Story ID | Epic | Title | Description | Acceptance Criteria | Priority | Effort | Status | Owner | Sprint | Dependencies | Notes
SPR-001 | E1 Auth & Users | Login with valid credentials | A registered user can authenticate and reach the protected dashboard. | • Given a valid username and password, when I submit the login form, then I am redirected to /dashboard • Given a successful login, when the dashboard renders, then my name appears in the sidebar footer • Given a successful login, when I open DevTools → Application → localStorage, then SPR_TECHFORGE_SESSION_V4 contains a userId and recent timestamp • Given a successful login, when I refresh the browser, then I remain logged in and the dashboard re-renders | P0 | 2 | Backlog | Tester 1 | S1
SPR-002 | E1 Auth & Users | Login with wrong password shows error | Entering a known username with the wrong password must fail clearly and stay on /login. | • Given a valid username and an incorrect password, when I submit, then an inline error "Invalid credentials" appears • Given the failed attempt, when the error is shown, then the URL is still /login • Given the failed attempt, when I inspect localStorage, then SPR_TECHFORGE_SESSION_V4 is NOT created • Given the failed attempt, when I retry with the correct password, then I am logged in normally | P0 | 1 | Backlog | Tester 1 | S1 | SPR-001
SPR-003 | E1 Auth & Users | Login with unknown username shows error | A username that does not exist in Firestore must fail with the same generic error (no user enumeration). | • Given a username that does not exist, when I submit, then "Invalid credentials" appears • Given a username that does not exist, when I submit, then the error wording is identical to the wrong-password case (no enumeration) • Given the failed attempt, when I check the network tab, then no /users/<id> read leaks the existence of the username | P0 | 1 | Backlog | Tester 1 | S1 | SPR-001
SPR-004 | E1 Auth & Users | Login form rejects empty fields | Submitting an empty username or password should be blocked client-side. | • Given both fields are empty, when I click Login, then a "Missing credentials" message appears OR the submit is blocked • Given only the username is filled, when I click Login, then the missing-password state is communicated • Given only the password is filled, when I click Login, then the missing-username state is communicated | P1 | 1 | Backlog | Tester 1 | S1
SPR-005 | E1 Auth & Users | Username is case-insensitive | The username comparison must lower-case both sides so users do not get locked out by capitalisation. | • Given a user created with username "Thirumal@sprtechforge.com", when I log in with "thirumal@sprtechforge.com", then I authenticate successfully • Given a user created with username "Tester1@test.com", when I log in with "TESTER1@TEST.COM", then I authenticate successfully | P1 | 1 | Backlog | Tester 1 | S1 | SPR-001
SPR-006 | E1 Auth & Users | Login attempt is recorded in activity log | Every successful login must produce an ActivityLog entry visible to the master user. | • Given a successful login, when the master opens /admin/logs, then an entry with action=LOGIN exists for this user with the current timestamp • Given a failed login, when the master opens /admin/logs, then no LOGIN entry is created (failures are not logged in the current build — confirm this is intentional) | P2 | 2 | Backlog | Tester 1 | S1 | SPR-001
SPR-007 | E1 Auth & Users | Logout returns to landing page | Sign out must clear the session and prevent access to protected routes. | • Given I am logged in, when I click Sign Out in the sidebar, then I land on / (landing page) • Given I have just logged out, when I try to navigate to /dashboard via URL, then I am redirected to /login • Given I have logged out, when I open DevTools → Application → localStorage, then SPR_TECHFORGE_SESSION_V4 is removed | P1 | 1 | Backlog | Tester 1 | S1 | SPR-001
SPR-008 | E1 Auth & Users | Session persists across browser refresh | Refreshing the page while logged in should keep me logged in. | • Given I am on /dashboard, when I press F5, then I remain on /dashboard • Given I am on /candidates, when I press F5, then I remain on /candidates with the list intact • Given I am logged in and close + reopen the tab within session timeout, then I am still authenticated | P1 | 1 | Backlog | Tester 1 | S1 | SPR-001
SPR-009 | E1 Auth & Users | Session expires after 60 minutes idle | Stale sessions must be invalidated so an unattended browser does not expose data. | • Given my session is older than 60 minutes (manipulate localStorage timestamp), when I refresh, then I am redirected to /login • Given an expired session, when I try to navigate to any protected route, then I am redirected to /login | P1 | 2 | Backlog | Tester 1 | S1 | SPR-001 | Clock manipulation via localStorage
SPR-010 | E1 Auth & Users | Bootstrap admin can log in on empty users collection | When Firestore has no users, the in-memory DEFAULT_ADMIN must accept login. | • Given the Firestore /users collection is empty, when I log in as thirumalreddy@sprtechforge.com / ThiruPriya@13, then I land on /dashboard • Given I am logged in as DEFAULT_ADMIN, when I view the sidebar, then the Finance group is visible (master privileges) | P0 | 1 | Backlog | Tester 1 | S1
SPR-011 | E1 Auth & Users | Bootstrap admin auto-persists when users collection is first populated | Regression of past production bug — adding a user must NOT wipe the bootstrap admin from in-memory state. | • Given Firestore /users is empty, when I log in as bootstrap admin and add another user via Admin → Users, then both users are present in Firestore /users • Given the bootstrap admin row now exists in Firestore, when I log out and back in as bootstrap admin, then login still succeeds • Given the bootstrap admin already exists in Firestore, when I open Admin → Users, then admin-01 is listed only once (no duplicates) | P0 | 1 | Backlog | Tester 1 | S1 | SPR-010 | Past prod incident — must remain green forever
SPR-012 | E1 Auth & Users | User can submit a password reset request | The "Forgot password" flow creates a PasswordResetRequest visible to the master for resolution. | • Given the login screen, when I click Forgot Password and submit my username, then a confirmation toast appears • Given a submitted reset request, when the master views the request list, then my username and request date appear with status=pending | P2 | 2 | Backlog | Tester 1 | S1
SPR-013 | E1 Auth & Users | Master can resolve a password reset request | The master can update a user's password from the reset request UI and mark the request resolved. | • Given a pending reset request, when the master enters a new password and clicks Resolve, then the user's password updates in Firestore • Given the request was resolved, when the user tries the new password on login, then they authenticate successfully • Given a resolved request, when re-listing requests, then the row shows status=resolved | P2 | 2 | Backlog | Tester 1 | S1 | SPR-012
SPR-014 | E1 Auth & Users | Admin adds a new user | Admin → Users → Add User must create a new Firestore /users document the new person can log in with. | • Given the Add User form with valid name/username/password/role, when I save, then the new user appears in the user list • Given the new user, when they log in with those credentials, then they reach /dashboard • Given the save, when an admin checks Activity Logs, then a CREATE entity=User action is logged | P0 | 3 | Backlog | Tester 1 | S1 | SPR-001
SPR-015 | E1 Auth & Users | Adding a user with a duplicate username is rejected | Same-username conflict must surface clearly without overwriting the existing user. | • Given a user with username "alice@test.com" exists, when an admin tries to add another user with the same username, then an inline error appears • Given the rejected save, when I refresh the user list, then only the original alice@test.com is present | P1 | 2 | Backlog | Tester 1 | S1 | SPR-014
SPR-016 | E1 Auth & Users | Admin edits a user | Editing a user's details must persist immediately and propagate everywhere the user appears. | • Given an existing user, when I change their name and save, then the new name shows in the list • Given the rename, when I open a chat the user wrote, then the message header reflects the new name • Given an admin edit, when Activity Logs is opened, then an UPDATE entity=User entry is present | P1 | 2 | Backlog | Tester 1 | S1 | SPR-014
SPR-017 | E1 Auth & Users | Admin can change a user's password | Admin can reset a user's password from the edit view; the user can immediately log in with the new value. | • Given an existing user, when an admin sets a new password and saves, then the user can log in with the new password • Given a password change, when the affected user is currently logged in, then their next protected request is unaffected within their active session (no forced logout in this build) | P2 | 2 | Backlog | Tester 1 | S1 | SPR-014
SPR-018 | E1 Auth & Users | Admin deletes a user | Delete removes the user from Firestore. Data they authored (chat messages) keeps the sender's name snapshot but the user is gone from the list. | • Given a regular staff user with no dependent finance records, when an admin deletes them and confirms, then they vanish from Admin → Users • Given the deletion, when the deleted user tries to log in, then login fails with Invalid credentials • Given the deletion, when an admin opens chats the deleted user wrote, then the historical messages still render with the senderName field on the message | P2 | 2 | Backlog | Tester 1 | S1 | SPR-014
SPR-019 | E1 Auth & Users | Admin assigns modules to a user | The modules array controls which sidebar groups the user sees. | • Given a staff user with modules=[candidates], when they log in, then only Overview and Candidates appear in the sidebar • Given a staff user with modules=[training,users], when they log in, then Overview, Training and Admin groups are visible • Given a candidate user (role=candidate), when they log in, then they see the student-portal nav regardless of modules | P1 | 2 | Backlog | Tester 1 | S1 | SPR-014
SPR-020 | E1 Auth & Users | Master role grants Finance access regardless of modules | Only the user whose username matches the master constant must see Finance routes. | • Given a user with username=thirumalreddy@sprtechforge.com, when they log in, then the Finance group is visible • Given another admin user with role=admin but a different username, when they log in, then the Finance group is hidden • Given a non-master user types /finance/dashboard into the URL directly, then they are redirected to /dashboard | P0 | 1 | Backlog | Tester 1 | S1 | SPR-001
SPR-021 | E1 Auth & Users | Master views the activity log | Only the master can open /admin/logs; the log shows the recent application actions. | • Given master role, when I open /admin/logs, then a chronological list of action entries appears • Given a non-master, when they type /admin/logs in the URL, then they are redirected to /dashboard • Given recent CRUD activity by any user, when the master opens logs, then the actions appear within 5 seconds (real-time Firestore subscription) | P1 | 2 | Backlog | Tester 1 | S1 | SPR-020
SPR-022 | E1 Auth & Users | Master can clear activity logs | A cleanup action removes all ActivityLog entries from Firestore. | • Given a populated activity log, when the master clicks Clear and confirms, then the activity log table is empty • Given the clear action, when the master refreshes, then the log stays empty until new actions are recorded • Given the clear, when the master adds a new user, then the next action recorded appears in the now-empty log | P2 | 2 | Backlog | Tester 1 | S1 | SPR-021
SPR-023 | E2 Candidates | Add a new candidate with required fields | The minimum-viable candidate (name, email, phone, batch, joinedDate, agreedAmount) saves successfully. | • Given the new-candidate form, when I fill the required fields and save, then the candidate appears in /candidates • Given the save, when I refresh, then the candidate persists in Firestore • Given the save, when I check Activity Logs as master, then a CREATE entity=Candidate entry is logged | P0 | 3 | Backlog | Tester 2 | S2 | SPR-014
SPR-024 | E2 Candidates | Add candidate with invalid email is rejected | Email validation prevents obvious garbage entries. | • Given the form, when I enter "notanemail" in the email field and submit, then an inline validation message appears and the save is blocked • Given the form, when I enter "test@" and submit, then the same validation triggers | P2 | 2 | Backlog | Tester 2 | S2 | SPR-023
SPR-025 | E2 Candidates | Edit candidate name | Renaming a candidate updates the list and any place the candidate name is shown. | • Given an existing candidate "John Doe", when I rename to "John D. Doe" and save, then /candidates shows the new name • Given the rename, when I open a related interview, then the candidate field reflects the new name • Given the rename, when Activity Logs is opened, then an UPDATE entity=Candidate entry is present | P1 | 2 | Backlog | Tester 2 | S2 | SPR-023
SPR-026 | E2 Candidates | Edit candidate contact details | Email, phone, alternate phone, and address are editable and persist. | • Given a candidate, when I change phone and save, then the phone is updated on re-open • Given a candidate, when I change email and save, then the candidate detail and address-book entries (if any) reflect the new email | P1 | 2 | Backlog | Tester 2 | S2 | SPR-025
SPR-027 | E2 Candidates | Edit candidate batch / status | Batch assignment and status transitions update the candidate and any dependent UI badges. | • Given a candidate in Training status, when I change to Placed and save, then the list filter "Placed" shows them • Given a candidate batch change, when I view the attendance sheet for the new batch, then the candidate appears there | P1 | 2 | Backlog | Tester 2 | S2 | SPR-023
SPR-028 | E2 Candidates | Delete candidate with no dependencies | A candidate with no interviews / transactions / training logs can be deleted. | • Given a candidate with no dependent records, when an admin deletes and confirms, then the candidate disappears from the list • Given the delete, when I refresh, then they remain gone • Given the delete, when Activity Logs is opened, then a DELETE entity=Candidate entry exists | P2 | 2 | Backlog | Tester 2 | S2 | SPR-023
SPR-029 | E2 Candidates | Delete candidate with linked records — behaviour confirmed | Define + verify the behaviour when deleting a candidate who has interviews, training logs, transactions. | • Given a candidate with linked transactions, when an admin attempts to delete, then the behaviour is consistent (allow OR block) and clearly documented • Given a deletion that orphans interview records, when I open the interviews list, then orphaned records are either hidden or marked | P2 | 3 | Backlog | Tester 2 | S2 | SPR-028 | Verify current behaviour and document it
SPR-030 | E2 Candidates | Search candidates by name | The candidate list supports text search by candidate name. | • Given >5 candidates with varied names, when I type "ali" in the search box, then only candidates whose name contains "ali" (case-insensitive) remain visible • Given a search query that matches no candidates, when I type, then an empty-state message appears • Given a search, when I clear the search, then all candidates re-appear | P2 | 2 | Backlog | Tester 2 | S2 | SPR-023
SPR-031 | E2 Candidates | Filter candidates by status | Filter dropdown narrows the list to a single CandidateStatus. | • Given candidates in multiple statuses, when I filter by Placed, then only Placed candidates show • Given the Placed filter, when I switch to Training, then the list updates accordingly • Given an empty status filter, when I clear, then all statuses are visible again | P2 | 2 | Backlog | Tester 2 | S2 | SPR-027
SPR-032 | E2 Candidates | Pagination on candidate list | When more than the page size of candidates exist, the list paginates without breaking. | • Given >20 candidates, when I open /candidates, then a pagination control appears • Given page 2, when I click Next, then a different batch of candidates is visible without duplicates | P3 | 2 | Backlog | Tester 2 | S2 | SPR-023 | If pagination is implemented; otherwise mark Won't Fix
SPR-033 | E2 Candidates | View candidate detail page | Clicking a candidate row opens a detail view with their bio, profile, status, finance, and training history. | • Given a candidate row, when I click the row, then I land on the candidate detail with all profile fields • Given the detail page, when I scroll, then I see linked interviews, training logs and transactions | P1 | 3 | Backlog | Tester 2 | S2 | SPR-023
SPR-034 | E2 Candidates | Complete candidate profile | CandidateProfile fields (DOB, address, education, experience) are editable and persist independently of the core candidate record. | • Given a candidate, when I fill DOB, education, skills and save, then the profile is stored in /candidateProfiles • Given a saved profile, when I re-open the profile page, then all fields are pre-populated | P1 | 3 | Backlog | Tester 2 | S2 | SPR-033
SPR-035 | E2 Candidates | Upload candidate resume | A PDF can be attached to a candidate and downloaded later. | • Given a candidate, when I upload a PDF resume, then a download link appears on the candidate detail • Given the upload, when I click the download link, then the same file opens or downloads • Given an uploaded resume, when I upload a replacement, then only the most recent version remains accessible | P2 | 2 | Backlog | Tester 2 | S2 | SPR-033
SPR-036 | E2 Candidates | Send agreement to candidate | The agreement flow records the send date and produces a portal link the candidate can use. | • Given a candidate with no agreement sent, when I click Send Agreement, then agreementSentDate is set on the record • Given the send, when I copy the portal link, then it opens the public agreement page for that candidate | P1 | 3 | Backlog | Tester 2 | S2 | SPR-023
SPR-037 | E2 Candidates | Candidate accepts agreement via portal | The candidate-facing portal lets the candidate accept the agreement, which writes agreementAcceptedDate. | • Given a portal link, when the candidate opens it (no login required) and clicks Accept, then agreementAcceptedDate is set • Given acceptance, when I view the candidate as admin, then the agreement status reflects Accepted | P1 | 3 | Backlog | Tester 2 | S2 | SPR-036
SPR-038 | E2 Candidates | Candidate rejects agreement with reason | Rejection records a reason and prevents further use of the same link until re-sent. | • Given a portal link, when the candidate clicks Reject with a reason and submits, then agreementRejectedDate and agreementRejectionReason are stored • Given a rejected agreement, when an admin views the candidate, then the rejection reason is visible • Given a rejected agreement, when admin re-sends, then a new agreementSentDate is recorded and the rejected timestamp clears | P2 | 3 | Backlog | Tester 2 | S2 | SPR-036
SPR-039 | E2 Candidates | Mark candidate as Placed with package details | When a candidate is placed, capture the company and package fields. | • Given a candidate, when I change status to Placed and fill placedCompany + packageDetails, then the data persists • Given a Placed candidate, when I view the candidate list, then the Placed badge and company appear in the row | P1 | 2 | Backlog | Tester 2 | S2 | SPR-027
SPR-040 | E2 Candidates | Work Support tracking | Active work-support assignments record dates and monthly amount. | • Given a Placed candidate, when I set workSupportStatus=Active with start/end dates and a monthly amount, then the data persists • Given an Active work-support candidate, when I view a candidate dashboard, then their support status is shown | P2 | 2 | Backlog | Tester 2 | S2 | SPR-039
SPR-041 | E3 Enquiries & Leads | Add a new enquiry | Capturing prospective leads via the Enquiries page creates an Enquiry record. | • Given the Enquiries page, when I add a new lead with name/phone/email/source, then it appears with status=Enquiry • Given the save, when I refresh, then the enquiry persists | P1 | 2 | Backlog | Tester 2 | S2
SPR-042 | E3 Enquiries & Leads | Add a note to an enquiry | Notes capture follow-up history per enquiry. | • Given an enquiry, when I add a note "Called, will join next batch", then the note appears in the enquiry timeline • Given multiple notes, when I view the enquiry, then notes are listed in chronological order with author and date | P2 | 2 | Backlog | Tester 2 | S2 | SPR-041
SPR-043 | E3 Enquiries & Leads | Update enquiry status | Status flow: Enquiry → Follow-Up → Joined or Not Interested. | • Given an enquiry in Enquiry status, when I move it to Follow-Up, then the status persists • Given a Follow-Up enquiry, when I move it to Joined, then the status updates and the merge action becomes available • Given a Follow-Up enquiry, when I mark Not Interested, then the row is visibly de-emphasised in the list | P1 | 2 | Backlog | Tester 2 | S2 | SPR-041
SPR-044 | E3 Enquiries & Leads | Merge a Joined enquiry into a new candidate | Merging promotes an enquiry into a full Candidate record. | • Given an enquiry in Joined status, when I click Merge to Candidate and confirm, then a new candidate is created with the enquiry's name/phone/email pre-filled • Given the merge, when I view the enquiry, then isMerged=true and a link to the new candidate is shown • Given a merged enquiry, when I try to merge again, then the action is disabled | P1 | 3 | Backlog | Tester 2 | S2 | SPR-043
SPR-045 | E3 Enquiries & Leads | Search enquiries | Free-text search filters enquiries by name, phone, or email. | • Given >5 enquiries, when I type "999" in search, then only enquiries with that substring in phone show • Given a search, when I clear it, then all enquiries re-appear | P2 | 2 | Backlog | Tester 2 | S2 | SPR-041
SPR-046 | E3 Enquiries & Leads | View web leads | External web-form submissions appear under Web Enquiries with an unread badge. | • Given a fresh web-lead Firestore doc, when I open Admin → Web Enquiries, then the lead shows with isRead=false • Given the sidebar, when an unread web lead exists, then a red unread count appears next to Web Enquiries | P2 | 2 | Backlog | Tester 2 | S2
SPR-047 | E3 Enquiries & Leads | Mark a web lead as read | Reading a web lead clears the badge and updates the status. | • Given an unread web lead, when I click into it, then isRead becomes true and the sidebar badge decrements • Given all web leads are read, when I refresh, then the sidebar badge disappears | P2 | 1 | Backlog | Tester 2 | S2 | SPR-046
SPR-048 | E3 Enquiries & Leads | Update web lead status | Web lead progress is tracked through New → In Progress → Responded → Closed. | • Given a New web lead, when I change to In Progress with an internal note, then both fields persist • Given Responded status, when I add a note, then the note is timestamped and visible in the row • Given a Closed lead, when filtering New leads, then the Closed lead is hidden | P2 | 2 | Backlog | Tester 2 | S2 | SPR-046
SPR-049 | E4 Training | Create a training module | Curriculum setup → add a module with title, description, and order. | • Given the curriculum page, when I add a module "React Fundamentals" with order=1, then it appears in the module list at position 1 • Given the save, when I refresh, then the module persists | P1 | 2 | Backlog | Tester 2 | S2
SPR-050 | E4 Training | Edit / reorder modules | Modules can be renamed and reordered. | • Given an existing module, when I edit the title and save, then the new title is visible • Given multiple modules, when I change the order field on one, then they re-sort in the curriculum view | P2 | 2 | Backlog | Tester 2 | S2 | SPR-049
SPR-051 | E4 Training | Add a topic under a module | Each module has one or more topics with estimated hours. | • Given a module, when I add a topic with title and estimatedHours, then it appears nested under the module • Given a topic, when I edit estimatedHours, then the value persists | P1 | 2 | Backlog | Tester 2 | S2 | SPR-049
SPR-052 | E4 Training | Record daily attendance | For a given date, the attendance sheet captures Present / Absent / No Class per candidate. | • Given today's date and >1 candidate, when I mark first Present and second Absent and save, then both entries persist • Given a saved day, when I revisit the same date, then the marks are pre-loaded • Given a save, when the master views Activity Logs, then a CREATE entity=TrainingLog entry is recorded | P0 | 3 | Backlog | Tester 2 | S2 | SPR-023
SPR-053 | E4 Training | Record assignment status alongside attendance | Each candidate row also captures assignmentStatus per day. | • Given a Present candidate, when I set assignmentStatus=Completed and save, then both attendance and assignment fields persist • Given an Absent candidate, when I save, then assignmentStatus defaults to N/A | P1 | 2 | Backlog | Tester 2 | S2 | SPR-052
SPR-054 | E4 Training | Track candidate progress (admin) | Progress Tracker aggregates per-candidate attendance + assignment metrics. | • Given attendance recorded over a week, when I open the Progress Tracker, then total days present and total assignments completed match the underlying logs • Given a candidate with multiple absences, when filtered, then the count of absent days is correct | P2 | 3 | Backlog | Tester 2 | S2 | SPR-052
SPR-055 | E4 Training | Candidate views their own training dashboard | Candidates with role=candidate land on a dashboard that shows only their data. | • Given a candidate logs in, when they view the student dashboard, then they see only their own attendance logs • Given the candidate dashboard, when scrolled, then upcoming interview details for this candidate appear | P1 | 2 | Backlog | Tester 2 | S2 | SPR-052
SPR-056 | E4 Training | View Curriculum (read-only) for candidates | Candidates see the published curriculum but cannot edit it. | • Given a candidate logs in, when they open Curriculum, then modules and topics render read-only • Given a candidate, when they look for add/edit/delete buttons, then none are present | P2 | 2 | Backlog | Tester 2 | S2 | SPR-049
SPR-057 | E5 Interviews | Schedule an interview | Creating an interview links a candidate to a date/time/company. | • Given a candidate exists, when I create an interview with date=tomorrow / time=11:00 / company=TestCo / type=Zoom / round=L1, then it appears under Scheduled • Given the save, when the sidebar shows the Interviews badge, then the count increments by 1 • Given the save, when the master views activity logs, then a CREATE entity=Interview is recorded | P0 | 3 | Backlog | Tester 2 | S2 | SPR-023
SPR-058 | E5 Interviews | Edit an interview | All interview fields are editable post-creation. | • Given a scheduled interview, when I change time and save, then the new time displays in the list • Given an edit, when an UPDATE log entry is checked, then the change is captured | P1 | 2 | Backlog | Tester 2 | S2 | SPR-057
SPR-059 | E5 Interviews | Mark interview outcome | Outcome can be Selected / Rejected / Pending. | • Given a Completed interview, when I set outcome=Selected, then the candidate (if not already Placed) is offered a follow-up to mark Placed • Given outcome=Rejected, when I view candidate dashboard, then rejection is reflected in interview history | P1 | 2 | Backlog | Tester 2 | S2 | SPR-057
SPR-060 | E5 Interviews | Reschedule an interview | Status flow: Scheduled → Rescheduled with new date/time. | • Given a Scheduled interview, when I reschedule to a new date and save, then status=Rescheduled and the new date displays • Given the reschedule, when sidebar badge re-renders, then "Today: N" reflects the new date | P1 | 2 | Backlog | Tester 2 | S2 | SPR-057
SPR-061 | E5 Interviews | Cancel an interview | Cancelled interviews are visibly de-emphasised and removed from upcoming counts. | • Given a Scheduled interview, when I cancel, then status=Cancelled and the row is greyed out • Given the cancel, when sidebar badge re-renders, then the upcoming count decrements | P1 | 2 | Backlog | Tester 2 | S2 | SPR-057
SPR-062 | E5 Interviews | Sidebar shows "Today: N" badge for interviews | Aggregated badge in the Training group reflects interviews scheduled for the current date. | • Given 2 interviews scheduled for today, when I view the sidebar, then "Today: 2" appears next to Interviews & Resumes • Given the day passes (date changes), when the page is loaded fresh, then today's count resets | P2 | 2 | Backlog | Tester 2 | S2 | SPR-057
SPR-063 | E5 Interviews | Manage interview question bank | CRUD on InterviewModules and InterviewQuestions. | • Given the Question Bank page, when I add a module "React" and add a question under it, then both persist • Given a question, when I edit and save, then the edit persists • Given a question, when I delete and confirm, then it is removed from the bank | P2 | 3 | Backlog | Tester 2 | S2
SPR-064 | E5 Interviews | Candidate runs an interview prep session | Candidates can practice answering questions; sessions are recorded. | • Given a candidate logs in, when they open Prompt Practice and run a session, then their responses are scored and a session record is saved to interviewPrepSessions • Given a completed session, when the candidate views past sessions, then they can replay each question with score and feedback | P2 | 3 | Backlog | Tester 2 | S2 | SPR-063
SPR-065 | E5 Interviews | View interview prep history (admin) | Admins/master can view past prep sessions per candidate. | • Given a candidate with prep sessions, when an admin opens the candidate detail, then the sessions list is visible with date and score | P3 | 2 | Backlog | Tester 2 | S2 | SPR-064
SPR-066 | E6 Finance | Add a Bank account | The master can add accounts of each AccountType. | • Given master role, when I add an account with name "HDFC Test", type Bank, openingBalance 100000, then it appears in /finance/accounts • Given an existing account, when I check Activity Logs, then a CREATE entity=Account entry exists | P0 | 2 | Backlog | Tester 3 | S3 | SPR-020
SPR-067 | E6 Finance | Add a Candidate / Debtor account | Debtor accounts represent candidates and link to their candidate id. | • Given a candidate exists, when I create a Debtor account linked to that candidate, then the account appears under Debtors • Given the link, when the candidate is renamed, then the Debtor account label updates accordingly | P1 | 2 | Backlog | Tester 3 | S3 | SPR-066
SPR-068 | E6 Finance | Edit an account | Account properties (name, sub-type, description) are editable. | • Given an account, when I edit its name and save, then the new name displays in /finance/accounts • Given the edit, when I open transactions referencing it, then those transactions show the new account name | P1 | 2 | Backlog | Tester 3 | S3 | SPR-066
SPR-069 | E6 Finance | Delete an account | Accounts with no transactions can be deleted; with transactions, deletion is blocked. | • Given an account with no transactions, when I delete and confirm, then it disappears • Given an account with transactions, when I attempt to delete, then I see a clear error explaining why and the account stays | P2 | 2 | Backlog | Tester 3 | S3 | SPR-066
SPR-070 | E6 Finance | Record an Income transaction | Income transactions credit a Bank account from a Debtor/Candidate. | • Given a Bank and a Candidate Debtor account, when I create Income of 25000 from candidate to bank, then both account balances reflect • Given the save, when I view /finance/transactions, then the new row appears at the top with date and amount | P0 | 3 | Backlog | Tester 3 | S3 | SPR-066
SPR-071 | E6 Finance | Record a Payment transaction | Payment debits a Bank account to an expense / creditor. | • Given a Bank account, when I record a Payment of 5000 to a Creditor, then the bank balance decreases by 5000 • Given the save, when I view the account statement, then the payment is visible with the correct sign | P0 | 2 | Backlog | Tester 3 | S3 | SPR-066
SPR-072 | E6 Finance | Record a Transfer between accounts | A Transfer moves funds between two internal accounts. | • Given two Bank accounts, when I transfer 10000 from A to B, then A decreases by 10000 and B increases by 10000 • Given the transfer, when I view both account statements, then matching entries appear in both with linked transaction id | P1 | 2 | Backlog | Tester 3 | S3 | SPR-066
SPR-073 | E6 Finance | Record a Refund transaction | Refunds reduce a candidate's paid amount and credit back to a Bank account. | • Given a candidate who paid 25000, when I record a Refund of 5000, then their paidAmount becomes 20000 • Given the refund, when I view the candidate's statement, then the refund row appears with negative sign | P2 | 2 | Backlog | Tester 3 | S3 | SPR-070
SPR-074 | E6 Finance | Lock a transaction | Locked transactions become non-editable and non-deletable. | • Given a transaction, when I click Lock and confirm, then the Edit and Delete buttons disappear or are disabled • Given a locked transaction, when I attempt to edit via direct URL or API, then the change is rejected • Given the lock, when I check Activity Logs, then a lock-related entry is recorded | P1 | 2 | Backlog | Tester 3 | S3 | SPR-070
SPR-075 | E6 Finance | Edit an unlocked transaction | Unlocked transactions can be corrected after creation. | • Given an unlocked transaction, when I change the amount and save, then both account balances re-compute • Given the edit, when I view Activity Logs, then an UPDATE entry is recorded | P1 | 2 | Backlog | Tester 3 | S3 | SPR-070
SPR-076 | E6 Finance | Delete an unlocked transaction | Deleting a transaction reverses its account balance effects. | • Given an unlocked income transaction, when I delete and confirm, then both account balances revert to pre-transaction state • Given the delete, when I view the candidate's statement, then the row no longer appears | P1 | 2 | Backlog | Tester 3 | S3 | SPR-070
SPR-077 | E6 Finance | View account statement | Account statements list all transactions touching the account with a running balance. | • Given an account with 5 transactions, when I open its statement, then all 5 appear in chronological order • Given the statement, when I read the rightmost column, then a running balance is computed correctly • Given the statement, when I export, then the same data downloads as an Excel file | P1 | 3 | Backlog | Tester 3 | S3 | SPR-070
SPR-078 | E6 Finance | Generate Balance Sheet | Financial Statements page generates a balance sheet that reconciles to the underlying transactions. | • Given some transactions, when I open Financial Statements → Balance Sheet, then total assets = total liabilities + equity • Given the report, when I drill into a line item, then the contributing transactions are shown | P1 | 3 | Backlog | Tester 3 | S3 | SPR-070
SPR-079 | E6 Finance | Generate Profit & Loss | P&L reconciles to income and expense transactions in the period. | • Given a date range, when I generate P&L, then total revenue and total expense match transactions in that range • Given a P&L, when I switch periods, then the totals update accordingly | P1 | 3 | Backlog | Tester 3 | S3 | SPR-078
SPR-080 | E6 Finance | Run payroll for a month | Payroll generates salary transactions for staff users. | • Given >1 staff users with salary accounts, when I run payroll for the current month, then a Payment txn is created against each salary account • Given a re-run, when the same month is selected, then duplicate entries are prevented OR clearly flagged | P2 | 3 | Backlog | Tester 3 | S3 | SPR-070
SPR-081 | E6 Finance | Export full financial report | Reports page exports a multi-sheet Excel with candidates, transactions, debtors, balance sheet, P&L. | • Given some data exists, when I click Export Full Report, then a .xls file downloads • Given the file, when I open in Excel, then the expected sheets (Candidates, Transactions, Sundry Debtors, Debts and Creditors, Balance Sheet, P&L) are present | P2 | 2 | Backlog | Tester 3 | S3 | SPR-077
SPR-082 | E6 Finance | Finance Dashboard reconciles with detail pages | Top-line cards on /finance/dashboard match underlying tables. | • Given some transactions, when I view the dashboard, then total revenue and total expense match those on the P&L for the same period • Given a refresh after a new transaction, when I check the dashboard, then the cards reflect the new transaction within seconds | P2 | 2 | Backlog | Tester 3 | S3 | SPR-070
SPR-083 | E6 Finance | Non-master cannot access Finance routes | Direct URL access to /finance/* is blocked for non-master users. | • Given a non-master admin, when they type /finance/transactions in URL, then they are redirected to /dashboard • Given a non-master, when they inspect the sidebar, then Finance group is not present | P0 | 1 | Backlog | Tester 3 | S3 | SPR-020
SPR-084 | E7 Chat | Start a DM with another user | The + button opens a user picker; selecting one creates or opens the DM. | • Given two users exist, when user A clicks + and picks user B, then a DM chat is created and selected • Given user A starts a DM with B, when user B opens chat, then the same DM is available (deterministic chat id) • Given an existing DM between A and B, when A tries to start a new DM with B, then the existing chat opens instead of creating a duplicate | P0 | 2 | Backlog | Tester 4 | S4 | SPR-014
SPR-085 | E7 Chat | Send a text message in a DM | Composer sends a message; both participants see it in real time. | • Given an active DM, when A sends "hi", then the bubble appears in A's thread immediately • Given B has the same DM open in another browser, when A sends, then the message appears within 3 seconds without B refreshing • Given B is on a different page when A sends, when B opens chat, then the unread badge is incremented and the new message is visible | P0 | 3 | Backlog | Tester 4 | S4 | SPR-084 | Two-browser test
SPR-086 | E7 Chat | Send a chat message with an image attachment | Images upload to Firebase Storage and render inline. | • Given a DM, when I attach an image <2MB and send, then the image renders inline in both A's and B's threads • Given the upload, when I check Firebase Storage at chats/{chatId}/, then the file exists with the original name • Given the image render, when I click the image, then it opens in a new tab at full size | P1 | 3 | Backlog | Tester 4 | S4 | SPR-085
SPR-087 | E7 Chat | Send a chat message with a non-image attachment | PDFs, docs, and other file types render as a download card. | • Given a DM, when I attach a PDF and send, then the bubble shows a file card with name and size • Given the card, when I click it, then the PDF opens or downloads | P1 | 2 | Backlog | Tester 4 | S4 | SPR-086
SPR-088 | E7 Chat | Composer keyboard shortcuts | Enter sends; Shift+Enter inserts a newline. | • Given the composer, when I type and press Enter, then the message is sent • Given the composer, when I press Shift+Enter, then a newline is inserted without sending | P2 | 1 | Backlog | Tester 4 | S4 | SPR-085
SPR-089 | E7 Chat | Unread badge per chat | Each chat row shows a count of messages I have not read. | • Given B sent 3 messages while A was on another page, when A opens chat, then the DM row shows badge=3 • Given A clicks the DM, when the messages load, then the badge clears and the messages are marked readBy=A • Given A on chat page B sends one more, when A is actively viewing that chat, then the badge does NOT appear | P1 | 2 | Backlog | Tester 4 | S4 | SPR-085
SPR-090 | E7 Chat | Sidebar Chat unread badge | Aggregated unread count appears next to Chat in the sidebar. | • Given >1 chat with unread messages, when I view the sidebar, then the badge shows the total unread count across visible chats • Given I open one chat and clear its unread, when I view the sidebar, then the badge decrements appropriately | P1 | 1 | Backlog | Tester 4 | S4 | SPR-089
SPR-091 | E7 Chat | Admin posts in Announcements channel | Only admins (or master) can post in Announcements; everyone reads. | • Given admin role, when I open Announcements, then the composer is visible • Given a non-admin, when they open Announcements, then a "Read-only" footer is shown instead of the composer • Given an admin post, when a non-admin opens the channel, then they see the message in real time | P1 | 2 | Backlog | Tester 4 | S4 | SPR-084
SPR-092 | E7 Chat | Announcements channel auto-creates on first open | The single global Announcements chat is created on first visit by any user. | • Given no announcement chat in Firestore, when I open Chat for the first time, then a chat with id "announcements-global" is created and selected by default • Given the auto-create, when the master views Firestore, then a single Announcements chat document exists | P2 | 1 | Backlog | Tester 4 | S4 | SPR-091
SPR-093 | E7 Chat | Chat list sorts by lastMessageAt | Most recently active chats float to the top. | • Given chats A, B, C with different lastMessageAt, when I view the chat list, then they sort with the most recent on top (Announcements pinned first) • Given a new message in chat C, when the list re-renders, then C moves to the top | P2 | 1 | Backlog | Tester 4 | S4 | SPR-085
SPR-094 | E7 Chat | Message ordering is stable | Messages within a chat appear in chronological order with no jumps when new ones arrive. | • Given a chat with 10 messages, when I scroll up and down, then no message changes position • Given a new message arrives, when the chat auto-scrolls to the bottom, then existing messages keep their relative order | P2 | 2 | Backlog | Tester 4 | S4 | SPR-085
SPR-095 | E7 Chat | Search users in New DM modal | The user picker filters by name or username. | • Given >5 users, when I type "alice" in the search, then only matching users remain • Given an empty query, when I open the picker, then all users (except me) are listed sorted alphabetically | P2 | 1 | Backlog | Tester 4 | S4 | SPR-084
SPR-096 | E8 Meetings | Schedule a new meeting | The + button opens a form to schedule a meeting with title / time / participants. | • Given the meetings page, when I fill title, start = tomorrow 10:00, end = 10:30, pick user B, and save, then the meeting appears under Tomorrow • Given the save, when I check the participant list on the new meeting, then I (organizer) have rsvp=accepted automatically • Given the save, when user B opens meetings, then they see the meeting with rsvp=pending | P0 | 3 | Backlog | Tester 4 | S4 | SPR-014
SPR-097 | E8 Meetings | Participant RSVPs Going | Accept button sets rsvp=accepted and propagates in real time. | • Given an invited participant, when they open the meeting and click Going, then their badge changes to Going • Given the RSVP change, when the organizer is also viewing the meeting, then the badge update appears within 3 seconds | P0 | 2 | Backlog | Tester 4 | S4 | SPR-096
SPR-098 | E8 Meetings | Participant RSVPs Maybe | Tentative RSVP is treated as a third state. | • Given an invited participant, when they click Maybe, then rsvp=tentative is stored and a yellow badge shows | P1 | 1 | Backlog | Tester 4 | S4 | SPR-097
SPR-099 | E8 Meetings | Participant declines | Declined RSVP marks the participant out and visually strikes them. | • Given an invited participant, when they click Declined, then rsvp=declined is stored and a red badge shows • Given a declined RSVP, when the organizer views the meeting, then "going count" decreases by one | P1 | 1 | Backlog | Tester 4 | S4 | SPR-097
SPR-100 | E8 Meetings | Edit a meeting | Organizer can change title, time, participants. | • Given a meeting I organized, when I change time and save, then the new time displays for all participants • Given a participant is removed, when I save, then they no longer see the meeting in their upcoming list • Given a new participant is added, when I save, then they receive the meeting with rsvp=pending | P1 | 2 | Backlog | Tester 4 | S4 | SPR-096
SPR-101 | E8 Meetings | Cancel a meeting | Cancelling sets status=cancelled and removes Join buttons. | • Given a meeting I organized, when I cancel and confirm, then status=cancelled and the meeting card shows a Cancelled badge • Given a cancelled meeting, when participants view it, then the Join button is hidden | P1 | 2 | Backlog | Tester 4 | S4 | SPR-096
SPR-102 | E8 Meetings | Permission to edit / cancel is enforced | Only organizer or master can edit/cancel. | • Given a meeting I did NOT organize, when I open it, then I see no Edit or Cancel buttons • Given master role, when I open any meeting, then Edit and Cancel are available regardless of organizer | P1 | 1 | Backlog | Tester 4 | S4 | SPR-100
SPR-103 | E8 Meetings | Today's meetings badge in sidebar | Sidebar badge under SPRConnect → Meetings shows count of meetings starting today. | • Given 2 meetings scheduled for today, when I view the sidebar, then "Today: 2" appears next to Meetings • Given a new meeting is added for today, when the sidebar re-renders, then the count increments to 3 | P2 | 1 | Backlog | Tester 4 | S4 | SPR-096
SPR-104 | E8 Meetings | Tabs filter meetings | Tabs: Upcoming, Organized by me, Past. | • Given a mix of meetings, when I click Upcoming, then only scheduled future meetings appear • Given the Organized by me tab, when I view it, then only meetings where I am organizer appear • Given the Past tab, when I view it, then completed/cancelled or past-end-time meetings appear | P2 | 2 | Backlog | Tester 4 | S4 | SPR-096
SPR-105 | E8 Meetings | Meeting card grouping by date | Meetings group under Today / Tomorrow / This week / Later. | • Given meetings on various dates, when I view Upcoming, then each meeting falls under the correct group header • Given today's meeting is past end-time, when I refresh, then it has moved to Past | P2 | 2 | Backlog | Tester 4 | S4 | SPR-104
SPR-106 | E8 Meetings | Schedule a meeting from a chat DM | The Schedule button in a DM header opens the meeting modal with the other user pre-selected. | • Given a DM with user B, when I click Schedule in the chat header, then the meeting modal opens with B pre-checked as a participant • Given I save the meeting, when user B opens meetings, then the new meeting is in their upcoming list | P2 | 2 | Backlog | Tester 4 | S4 | SPR-096
SPR-107 | E8 Meetings | Validation: end time must be after start time | Form prevents saving meetings where end <= start. | • Given the new meeting form, when I set end-time <= start-time and click Save, then an inline error appears and the save is blocked | P2 | 1 | Backlog | Tester 4 | S4 | SPR-096
SPR-108 | E9 Video Calls | Start a video call from a DM | The Call button in DM chat header navigates to /call and creates an invitation. | • Given a DM with user B, when I click Call, then I am taken to /call/<roomId> and a Jitsi iframe loads • Given the call start, when I check Firestore /callInvitations, then a row with callerId=me and calleeId=B exists with status=ringing | P0 | 3 | Backlog | Tester 4 | S4 | SPR-084
SPR-109 | E9 Video Calls | Callee sees the ring overlay regardless of page | The IncomingCallOverlay component is mounted globally and rings whenever a CallInvitation arrives. | • Given user B is on /candidates when A calls, when the invitation is created, then B sees a full-screen ring overlay within 3 seconds • Given the overlay, when B looks at it, then it shows A's name and Accept / Decline buttons • Given the overlay, when B is in another tab, then a short ringtone (browser audio) plays | P0 | 3 | Backlog | Tester 4 | S4 | SPR-108 | Two-browser test
SPR-110 | E9 Video Calls | Callee accepts the call | Accept marks the invitation accepted and navigates to /call. | • Given a ringing call, when B clicks Accept, then B is navigated to /call/<roomId> • Given both A and B are in the room, when they look at Jitsi, then they see each other's video (after Google sign-in on A side) • Given the accept, when the invitation is checked, then status=accepted | P0 | 2 | Backlog | Tester 4 | S4 | SPR-109
SPR-111 | E9 Video Calls | Callee declines the call | Decline updates the invitation and notifies the caller. | • Given a ringing call, when B clicks Decline, then the ring overlay closes • Given the decline, when A is still on /call, then A sees a toast "B declined the call" and is navigated back to /chat • Given the decline, when the invitation is checked, then status=declined | P1 | 2 | Backlog | Tester 4 | S4 | SPR-109
SPR-112 | E9 Video Calls | Ring overlay auto-hides after 45s (TTL) | Stale invitations should not ring forever. | • Given a ringing call, when B does nothing for 45 seconds, then the overlay disappears on B's side • Given the timeout, when the invitation is checked, then status remains ringing in Firestore (caller-side cleanup is acceptable) | P2 | 1 | Backlog | Tester 4 | S4 | SPR-109
SPR-113 | E9 Video Calls | Join a scheduled meeting via video | The Join button on a meeting card opens the meeting's Jitsi room. | • Given a meeting I am invited to is in Scheduled status, when I click Join on the card, then I am taken to /call with the meeting title pre-set • Given two invitees click Join, when they both load, then they meet in the same Jitsi room | P0 | 2 | Backlog | Tester 4 | S4 | SPR-096
SPR-114 | E9 Video Calls | Leave call returns to source page | The Leave button on /call returns the user to the chat or meeting page. | • Given I am in a call started from /chat, when I click Leave, then I return to /chat • Given the leave, when I am the caller, then the invitation is marked status=ended | P1 | 1 | Backlog | Tester 4 | S4 | SPR-108
SPR-115 | E9 Video Calls | Jitsi readyToClose event also triggers leave | If a user hangs up via Jitsi's own UI, the app should also clean up. | • Given I am in a Jitsi call, when I click Jitsi's native Hang Up button, then I return to the source page automatically • Given the readyToClose, when I check the invitation, then status=ended | P2 | 2 | Backlog | Tester 4 | S4 | SPR-114
SPR-116 | E9 Video Calls | Cannot call yourself | Self-call attempts are blocked. | • Given I am in my own DM (somehow), when I click Call, then a clear error is shown and no invitation is created | P3 | 1 | Backlog | Tester 4 | S4 | SPR-108
SPR-117 | E9 Video Calls | Ringing overlay does not appear when in a call | Suppress the overlay while the user is on /call/* to avoid call-over-call confusion. | • Given I am in a call, when another user calls me, then the ring overlay does NOT appear in the current /call page • Given the missed call, when I leave the call, then if the invitation is still within TTL, the overlay shows; otherwise nothing appears | P2 | 2 | Backlog | Tester 4 | S4 | SPR-109
SPR-118 | E10 Email | Email page shows configured state | When env vars are present, the inbox loads. | • Given VITE_EMAIL_ENDPOINT and SECRET are set in the build, when I open Email, then the inbox renders (loading then list) • Given a valid response, when the page loads, then no "not configured" message appears | P0 | 2 | Backlog | Tester 3 | S3
SPR-119 | E10 Email | Email page shows not-configured fallback | If env vars are missing, a friendly message points to SETUP-EMAIL.md. | • Given VITE_EMAIL_ENDPOINT is empty, when I open Email, then the "Email isn't configured yet" card appears • Given the fallback, when I open DevTools, then no JS errors are present | P0 | 1 | Backlog | Tester 3 | S3 | SPR-118
SPR-120 | E10 Email | Inbox loads and auto-refreshes | Polling every 30 seconds fetches the latest inbox messages. | • Given the email bridge is configured, when I open Email, then the inbox loads within 5 seconds • Given I leave the page open, when 30 seconds pass, then the refresh icon spins and the list updates if new mail arrived • Given I click the refresh icon manually, when the request completes, then the list updates immediately | P0 | 3 | Backlog | Tester 3 | S3 | SPR-118
SPR-121 | E10 Email | Send a plain text email | Compose form sends via the GAS bridge using Gmail. | • Given the compose form, when I fill To/Subject/Body and click Send, then a success toast appears • Given the send, when the recipient checks their inbox, then they receive the email from the configured Gmail address • Given the send, when I check Activity Logs as master, then a CREATE entity=Email entry is recorded | P0 | 3 | Backlog | Tester 3 | S3 | SPR-118
SPR-122 | E10 Email | Send email with multiple attachments | Files upload to Firebase Storage and the GAS fetches them back to attach. | • Given a compose with a small image and a small PDF attached, when I send, then the recipient receives both files intact • Given the upload, when I check Firebase Storage at emails/outbound/, then the files exist | P1 | 3 | Backlog | Tester 3 | S3 | SPR-121
SPR-123 | E10 Email | Reject sending if To/Subject/Body missing | Validation prevents partial emails. | • Given the compose form, when To is empty and I click Send, then an error toast appears and no send occurs • Given an empty Body, when I click Send, then an error toast appears | P2 | 1 | Backlog | Tester 3 | S3 | SPR-121
SPR-124 | E10 Email | Send to multiple recipients (comma-separated) | Multiple addresses in the To field deliver to all. | • Given To = "a@test.com, b@test.com", when I send, then both addresses receive the email | P2 | 1 | Backlog | Tester 3 | S3 | SPR-121
SPR-125 | E10 Email | Reply to an inbox message | Reply pre-fills To, Re: subject, and quoted body. | • Given an inbox message, when I click Reply, then the compose modal opens with sender's address in To • Given the reply, when the subject is pre-filled, then it has "Re: " prefix (not double "Re: Re:" if original was already "Re: ...") • Given the reply, when the body pre-fills, then the original message snippet is quoted at the bottom | P1 | 2 | Backlog | Tester 3 | S3 | SPR-120
SPR-126 | E10 Email | Search the inbox | Free-text search filters visible messages. | • Given >5 inbox messages, when I type a sender name in the search, then only matching rows remain • Given a search that matches no rows, when I clear search, then all messages re-appear | P2 | 2 | Backlog | Tester 3 | S3 | SPR-120
SPR-127 | E10 Email | Bad shared secret returns error | Tampered or missing secret yields a clear error from GAS. | • Given VITE_EMAIL_SHARED_SECRET is wrong, when I open Email, then an error banner appears in the inbox • Given the same wrong secret, when I try Send, then a clear error toast appears explaining the bridge rejected the request | P2 | 1 | Backlog | Tester 3 | S3 | SPR-118
SPR-128 | Cross-cutting | Tablet layout (1024px) | All top-level pages remain usable at 1024×768. | • Given a tablet viewport, when I navigate dashboard, candidates, training, chat, meetings, email, then nothing overflows horizontally • Given the viewport, when I open the chat thread + sidebar, then both panels remain readable | P2 | 3 | Backlog | Tester 1 | S5
SPR-129 | Cross-cutting | Phone layout (375px) | Mobile menu replaces the sidebar; main content remains readable. | • Given a phone viewport, when I open any page, then the hamburger menu shows and the sidebar is hidden • Given the phone view, when I open the chat, then the conversation list and thread stack vertically and remain usable | P2 | 3 | Backlog | Tester 1 | S5 | SPR-128
SPR-130 | Cross-cutting | Smoke pass on Chrome (Tier 1) | The full smoke checklist passes on Chrome latest. | • Given the latest QA build, when I run smoke on Chrome (login → dashboard → candidates → chat → meeting → email), then all checks pass with no console errors | P0 | 2 | Backlog | Tester 1 | S5
SPR-131 | Cross-cutting | Smoke pass on Edge (Tier 1) | Same smoke checklist passes on Edge latest. | • Given the latest QA build, when I run smoke on Edge, then all checks pass with no console errors | P0 | 2 | Backlog | Tester 1 | S5 | SPR-130
SPR-132 | Cross-cutting | Smoke pass on Firefox (Tier 2) | Same smoke checklist on Firefox. | • Given the latest QA build, when I run smoke on Firefox, then all checks pass; visual differences (if any) are documented but not blockers | P1 | 2 | Backlog | Tester 1 | S5 | SPR-130
SPR-133 | Cross-cutting | Real-time sync across two browsers | Firestore listeners propagate changes across sessions reliably. | • Given two browsers logged in as A and B, when A adds a candidate, then B (already on /candidates) sees the new candidate within 5 seconds without refresh • Given the same setup, when B updates the same candidate's name, then A sees the change within 5 seconds | P0 | 2 | Backlog | Tester 1 | S5
SPR-134 | Cross-cutting | No JS errors in production console | A clean DevTools console is a P1 quality gate. | • Given any top-level page, when I open DevTools console and reload, then no red errors appear • Given a happy-path action (e.g., add candidate), when it completes, then no console errors are logged | P1 | 2 | Backlog | Tester 1 | S5
SPR-135 | Cross-cutting | Activity log entries are accurate and complete | All CRUD operations produce a log entry; the actor identity is correct. | • Given each major action (add user, add candidate, schedule interview, lock txn, send email), when performed, then a log entry exists with actorId, action, entityType, entityId • Given an action by user A while B is also logged in, when the log entry is recorded, then actorId points to A (not the bootstrap admin) | P1 | 3 | Backlog | Tester 1 | S5
SPR-136 | Cross-cutting | Keyboard navigation through key forms | Tab/Shift+Tab moves focus predictably; Enter submits forms. | • Given a form (login, new candidate, new meeting), when I Tab through, then focus moves in a logical order and the active field is visually indicated • Given the form is fully filled, when I press Enter, then the primary action triggers (Save / Send / Login) | P2 | 2 | Backlog | Tester 1 | S5
SPR-137 | Cross-cutting | No data leak between QA and production | Verify QA reads/writes are confined to sprtechforge-qa Firestore, not sprtechforge. | • Given the QA build, when I add a candidate on QA, then the new candidate appears in Firebase Console sprtechforge-qa only • Given the same action, when I check Firebase Console sprtechforge (prod), then the data is NOT present | P0 | 1 | Backlog | Tester 1 | S5
SPR-138 | E2 Candidates | Address book lists candidates with contact details | The Address Book page presents a quick directory. | • Given several candidates, when I open Address Book, then each candidate appears with name, phone, email • Given a candidate with an empty email, when listed, then the missing field is rendered as a dash (not "undefined") | P2 | 2 | Backlog | Tester 2 | S2 | SPR-023
SPR-139 | E2 Candidates | Address book search and copy | Address book is searchable and supports click-to-copy. | • Given the address book, when I type a partial phone, then matching rows remain • Given a row, when I click the phone field, then it copies to clipboard with a toast confirmation | P3 | 2 | Backlog | Tester 2 | S2 | SPR-138
SPR-140 | E2 Candidates | Candidate notes are persisted | A free-text notes field per candidate captures internal commentary. | • Given a candidate, when I add notes and save, then the notes persist across refresh • Given subsequent edits, when I save, then the latest content overwrites the old | P2 | 1 | Backlog | Tester 2 | S2 | SPR-025
SPR-141 | E1 Auth & Users | Master can change Firebase config via Cloud Setup | Cloud Setup page accepts a manual Firebase config override stored in localStorage. | • Given master role, when I open /admin/cloud, then the current Firebase project ID is shown • Given I save a new config, when the page reloads, then the app initialises against the new project (smoke test only — do not switch to prod) | P3 | 3 | Backlog | Tester 3 | S3 | SPR-020
SPR-142 | E1 Auth & Users | Master can run the in-app Test Runner | Test Runner page exercises a hard-coded set of validations and reports pass/fail. | • Given master role, when I open /admin/test-runner and run, then results are reported per test with pass/fail/skip • Given a failure, when the page renders results, then the failure reason is shown clearly | P3 | 2 | Backlog | Tester 3 | S3 | SPR-020

## Test Cases
TC ID | Story ID | Title | Type | Pre-conditions | Test Steps | Test Data | Expected Result | Priority | Status | Owner | Notes
TC-001 | SPR-001 | Login with valid bootstrap admin | Functional | QA URL reachable; bootstrap admin exists in code or Firestore | 1. Open https://sprtechforge-qa.web.app 2. Click Sign In 3. Enter username thirumalreddy@sprtechforge.com 4. Enter password ThiruPriya@13 5. Click Login | Username: thirumalreddy@sprtechforge.com / Password: ThiruPriya@13 | Redirected to /dashboard; sidebar shows user name; SPR_TECHFORGE_SESSION_V4 in localStorage; Finance group visible (master) | P0 | Active | Tester 1
TC-002 | SPR-002 | Login with wrong password | Negative | QA URL reachable | 1. Go to /login 2. Enter valid username 3. Enter incorrect password 4. Click Login | Username: thirumalreddy@sprtechforge.com / Password: WrongPass123 | Inline error "Invalid credentials"; URL stays /login; no SESSION_KEY written | P0 | Active | Tester 1
TC-003 | SPR-003 | Login with unknown username | Negative | QA URL reachable | 1. Go to /login 2. Enter non-existent username 3. Enter any password 4. Click Login | Username: ghost@example.com / Password: anything | Same generic "Invalid credentials" error (no enumeration) | P0 | Active | Tester 1
TC-004 | SPR-004 | Login with empty fields | Negative | QA URL reachable | 1. Go to /login 2. Leave both fields blank 3. Click Login | None | Form-level validation prevents submit OR returns "Missing credentials" error | P1 | Active | Tester 1
TC-005 | SPR-005 | Username login is case-insensitive | Functional | A user exists with username "Tester1@test.com" | 1. Go to /login 2. Enter username "TESTER1@TEST.COM" 3. Enter correct password 4. Click Login | Tester1@test.com with mixed-case input | Login succeeds; dashboard renders | P1 | Active | Tester 1
TC-006 | SPR-007 | Logout returns to landing | Functional | Logged in as any user | 1. Click Sign Out in the sidebar 2. Try navigating to /dashboard via URL bar | None | Lands on /; visiting /dashboard redirects to /login; SESSION_KEY removed | P1 | Active | Tester 1
TC-007 | SPR-008 | Session persists across refresh | Functional | Logged in as any user | 1. Log in 2. Navigate to /candidates 3. Press F5 to reload 4. Wait for app to load | None | User remains on /candidates after reload; sidebar still shows their name | P1 | Active | Tester 1
TC-008 | SPR-009 | Session expires after 60 min idle | Functional | Logged in as any user; DevTools open | 1. Log in 2. Open Application > localStorage 3. Edit SPR_TECHFORGE_SESSION_V4 to set timestamp 70 min ago 4. Refresh | Modified session timestamp | User redirected to /login | P1 | Active | Tester 1 | Clock manipulation via localStorage
TC-009 | SPR-010 | Bootstrap admin login on empty users collection | Functional | Firestore /users collection is empty (delete docs manually in Firebase Console) | 1. Confirm /users is empty 2. Open QA URL 3. Log in as bootstrap admin | thirumalreddy@sprtechforge.com / ThiruPriya@13 | Login succeeds; dashboard renders; master features visible | P0 | Active | Tester 1
TC-010 | SPR-011 | Bootstrap admin auto-persists regression | Regression | Firestore /users collection is empty | 1. Log in as bootstrap admin (empty collection) 2. Go to Admin > Users > Add User 3. Save a new user with role=staff 4. Refresh and check Firestore /users in Firebase Console | New user: name "Tester One", username "t1@test.com", role staff | Both admin-01 AND the new user exist in /users; bootstrap login still works after logout/login | P0 | Active | Tester 1 | Past prod bug fix
TC-011 | SPR-014 | Admin adds a new user | Functional | Logged in as admin | 1. Admin > Users > Add User 2. Fill name "Test Tester", username "tester@test.com", password "Test@1234", role staff, modules [candidates,training] 3. Save 4. Logout; log in as the new user | Provided in steps | New user appears in the list; they log in and see only Overview+Candidates+Training in sidebar | P0 | Active | Tester 1
TC-012 | SPR-015 | Duplicate username rejected | Negative | A user with username "alice@test.com" exists | 1. Add User 2. Try to create another user with username "alice@test.com" 3. Save | Duplicate username | Inline error; original user remains; no new user created | P1 | Active | Tester 1
TC-013 | SPR-016 | Admin edits user; rename reflects in chat | Integration | A user exists who has sent a chat message | 1. Admin > Users > Edit 2. Change name from "Alice" to "Alice K." 3. Save 4. Open the chat where that user sent a message | Rename target user | List shows new name; chat message header reflects "Alice K." | P1 | Active | Tester 1
TC-014 | SPR-018 | Admin deletes a user | Functional | A non-master regular user exists with no dependent finance records | 1. Admin > Users 2. Delete the user with confirmation 3. Verify they cannot log in 4. Refresh user list | Target user | User gone from list; login fails for them; their historical chats keep the senderName field | P2 | Active | Tester 1
TC-015 | SPR-019 | Module assignment controls sidebar | Authorization | A staff user exists | 1. Edit user, set modules=[training] only 2. Save 3. Log in as that user 4. Inspect sidebar | modules=[training] | Only Overview, SPRConnect and Training groups visible; Candidates/Admin hidden | P1 | Active | Tester 1
TC-016 | SPR-020 | Master vs non-master Finance access | Authorization | Both a master user and a non-master admin exist | 1. Log in as master; verify Finance group present and /finance/dashboard opens 2. Log out; log in as a non-master admin 3. Verify Finance is hidden; try /finance/dashboard URL | Two users | Master can access Finance; non-master cannot see it and is redirected to /dashboard | P0 | Active | Tester 1
TC-017 | SPR-021 | Master views activity log | Functional | Master user logged in; some activity already exists in Firestore /activityLogs | 1. Open /admin/logs 2. Inspect the table | None | Recent actions appear with timestamp, actorName, action, entityType | P1 | Active | Tester 1
TC-018 | SPR-023 | Add a new candidate | Functional | Logged in as admin | 1. Candidates > New 2. Fill name "John Doe", email "john@test.com", phone +91-9999999999, batch B1, joinedDate today, agreedAmount 50000 3. Save | Provided | Candidate appears in /candidates list; refresh preserves; CREATE log present | P0 | Active | Tester 2
TC-019 | SPR-024 | Add candidate with invalid email | Negative | Logged in as admin | 1. New Candidate form 2. Enter email "notanemail" 3. Try to save | Invalid email | Inline validation error; save blocked | P2 | Active | Tester 2
TC-020 | SPR-025 | Edit candidate name | Functional | A candidate "John Doe" exists | 1. Open candidate 2. Change name to "John D. Doe" 3. Save 4. View list | Rename target | List shows new name; opening candidate again shows new name; UPDATE log present | P1 | Active | Tester 2
TC-021 | SPR-027 | Change candidate status to Placed | Functional | A candidate in Training status exists | 1. Edit candidate 2. Change status from Training to Placed 3. Set placedCompany "TestCo" and packageDetails "5 LPA" 4. Save | Status change | List filter "Placed" shows the candidate; placedCompany visible in detail | P1 | Active | Tester 2
TC-022 | SPR-030 | Search candidates by name | Functional | >5 candidates exist with varied names | 1. /candidates 2. Type "ali" in search box 3. Observe filtered list 4. Clear search | Search query "ali" | Only candidates whose name contains "ali" (case-insensitive) remain; clearing brings all back | P2 | Active | Tester 2
TC-023 | SPR-035 | Upload and download resume | Functional | A candidate exists | 1. Open candidate 2. Upload a small PDF resume 3. Refresh 4. Click the resume download link | Small PDF (<1MB) | PDF uploads; reopening candidate shows resume; download returns the same file | P2 | Active | Tester 2
TC-024 | SPR-036 | Send agreement to candidate | Functional | A candidate with no agreement sent exists | 1. Open candidate 2. Click Send Agreement 3. Confirm 4. Copy the portal link | None | agreementSentDate set to today; portal link generated and accessible | P1 | Active | Tester 2
TC-025 | SPR-037 | Candidate accepts agreement via portal | Functional | Agreement has been sent to a candidate | 1. Open the portal link in incognito browser 2. Read agreement 3. Click Accept | Portal link from TC-024 | agreementAcceptedDate recorded; portal shows confirmation; admin sees Accepted status | P1 | Active | Tester 2
TC-026 | SPR-038 | Candidate rejects agreement | Functional | Agreement has been sent | 1. Open the portal link in incognito 2. Click Reject 3. Enter reason "Salary expectation mismatch" 4. Submit | Rejection reason | agreementRejectedDate and reason saved; admin view shows rejected status with the reason | P2 | Active | Tester 2
TC-027 | SPR-041 | Add a new enquiry | Functional | Logged in as admin | 1. Open /candidates/enquiry 2. Click Add Enquiry 3. Fill name, phone, email, source 4. Save | Sample enquiry data | Enquiry appears in list with status=Enquiry; persists on refresh | P1 | Active | Tester 2
TC-028 | SPR-042 | Add note to enquiry | Functional | An enquiry exists | 1. Open the enquiry 2. Add note "Called; following up next week" 3. Save | Sample note | Note appears in the enquiry timeline with author and current date | P2 | Active | Tester 2
TC-029 | SPR-043 | Move enquiry through statuses | Functional | An enquiry in Enquiry status exists | 1. Open the enquiry 2. Change status to Follow-Up 3. Add a note 4. Change to Joined | Status transitions | Each status change persists and is visible on refresh | P1 | Active | Tester 2
TC-030 | SPR-044 | Merge enquiry into candidate | Integration | An enquiry in Joined status exists | 1. Open enquiry 2. Click Merge to Candidate 3. Confirm 4. Navigate to /candidates and find the new candidate | None | New candidate created with enquiry data; enquiry shows isMerged=true with link to candidate | P1 | Active | Tester 2
TC-031 | SPR-046 | View web leads with unread badge | Functional | At least one web lead exists in Firestore with isRead=false | 1. Look at sidebar; verify Web Enquiries badge count 2. Open Admin > Web Enquiries | None | Sidebar shows unread count; opening the page shows the lead in the list | P2 | Active | Tester 2
TC-032 | SPR-047 | Mark a web lead as read | Functional | An unread web lead exists | 1. Click into the unread lead 2. View again and check sidebar badge | None | isRead becomes true; sidebar badge decrements | P2 | Active | Tester 2
TC-033 | SPR-049 | Create a training module | Functional | Logged in as admin | 1. Training > Curriculum Setup 2. Add Module "React Fundamentals", order 1 3. Save | Module name and order | Module appears at position 1 in the curriculum view | P1 | Active | Tester 2
TC-034 | SPR-051 | Add a topic under a module | Functional | A module exists | 1. Open module 2. Add topic "JSX basics", estimatedHours 2 3. Save | Topic name + hours | Topic nested under module with the entered estimatedHours | P1 | Active | Tester 2
TC-035 | SPR-052 | Record daily attendance | Functional | Candidates exist | 1. Training > Daily Attendance 2. Pick today 3. Mark first candidate Present, second Absent 4. Save 5. Re-open same date | Two candidates | Both saves persist; same selections re-load on revisit | P0 | Active | Tester 2
TC-036 | SPR-053 | Record assignment status alongside attendance | Functional | A Present candidate exists for today | 1. Open attendance for today 2. For Present candidate set assignmentStatus=Completed 3. Save | Assignment completion | Both fields persist on the TrainingLog | P1 | Active | Tester 2
TC-037 | SPR-054 | Progress tracker aggregates correctly | Functional | Attendance has been recorded for a candidate over multiple days | 1. Open Training > Progress Tracker 2. Find the candidate 3. Compare totals with underlying logs | Multi-day logs | Totals (days present, completed assignments) match the underlying training logs | P2 | Active | Tester 2
TC-038 | SPR-055 | Candidate sees only their own training | Authorization | A candidate user exists with attendance records | 1. Log in as the candidate 2. Open Training Dashboard 3. Inspect what is visible | Candidate logged in | Only their own attendance + interview schedule appear; no other candidates visible | P1 | Active | Tester 2
TC-039 | SPR-057 | Schedule an interview | Functional | A candidate exists; logged in as admin | 1. Interviews > Schedule 2. Pick candidate 3. Date=tomorrow, time=11:00, company=TestCo, type=Zoom, round=L1 4. Save 5. Check sidebar badge | Provided | Interview appears under Scheduled tomorrow; sidebar Interviews badge increments | P0 | Active | Tester 2
TC-040 | SPR-058 | Reschedule an interview | Functional | A scheduled interview exists | 1. Open the interview 2. Change date to day-after-tomorrow 3. Save | New date | Status changes to Rescheduled; new date displayed; badge re-counts | P1 | Active | Tester 2
TC-041 | SPR-061 | Cancel an interview | Functional | A scheduled interview for today exists | 1. Open the interview 2. Cancel 3. Look at sidebar today badge | None | Status=Cancelled; row visibly de-emphasised; sidebar Today badge decrements | P1 | Active | Tester 2
TC-042 | SPR-063 | Manage interview question bank | Functional | Logged in as admin | 1. Interview Question Bank 2. Add module "React" 3. Add a question under it 4. Edit the question 5. Delete the question | Question text | Each CRUD step persists and the list updates accordingly | P2 | Active | Tester 2
TC-043 | SPR-066 | Add a Bank account | Functional | Logged in as master | 1. Finance > Accounts > Add 2. Name "HDFC Test", type Bank, openingBalance 100000 3. Save | Provided | Account appears in Chart of Accounts with the opening balance | P0 | Active | Tester 3
TC-044 | SPR-070 | Record income transaction | Functional | A Bank account and a Candidate Debtor account both exist | 1. Finance > Transactions > New 2. Type Income, amount 25000, from candidate to bank 3. Save 4. Compare account balances | Income 25000 | Bank +25000; Debtor changes appropriately; transaction visible in register | P0 | Active | Tester 3
TC-045 | SPR-071 | Record payment transaction | Functional | A Bank account exists with positive balance; a Creditor account exists | 1. Finance > Transactions > New 2. Type Payment, amount 5000, from bank to creditor 3. Save | Payment 5000 | Bank -5000; Creditor balance reflects; row appears in register | P0 | Active | Tester 3
TC-046 | SPR-072 | Transfer between bank accounts | Functional | Two Bank accounts exist with balances | 1. Transactions > New 2. Type Transfer, amount 10000, from A to B 3. Save | Transfer 10000 | A balance -10000; B balance +10000; entries appear on both statements with the same linked transaction id | P1 | Active | Tester 3
TC-047 | SPR-074 | Lock a transaction prevents edits | Authorization | At least one transaction exists | 1. Open a transaction 2. Click Lock and confirm 3. Try to Edit or Delete | None | Edit/Delete disabled or rejected; activity log entry for the lock | P1 | Active | Tester 3
TC-048 | SPR-075 | Edit an unlocked transaction | Functional | An unlocked income transaction exists | 1. Open transaction 2. Change amount from 25000 to 30000 3. Save 4. Verify both account balances | New amount | Both impacted balances recompute; UPDATE log entry recorded | P1 | Active | Tester 3
TC-049 | SPR-076 | Delete an unlocked transaction | Functional | An unlocked income transaction exists | 1. Open transaction 2. Click Delete and confirm 3. Verify account balances | None | Both impacted balances revert; transaction no longer in register | P1 | Active | Tester 3
TC-050 | SPR-077 | View account statement | Functional | An account with at least 3 transactions exists | 1. Finance > Accounts > Open the account 2. Open Statement 3. Read each row's running balance | None | Transactions in order; running balance is correct at each row | P1 | Active | Tester 3
TC-051 | SPR-078 | Balance sheet reconciles | Functional | Some transactions exist; logged in as master | 1. Finance > Financial Reports 2. View Balance Sheet 3. Verify Assets = Liabilities + Equity | None | Totals reconcile to underlying data; no orphan entries | P1 | Active | Tester 3
TC-052 | SPR-079 | P&L reconciles by date range | Functional | Income + expense transactions in current month | 1. Open Financial Reports > P&L 2. Pick current month 3. Compare totals with the transactions sheet | Current-month range | Total revenue and total expense match the underlying transactions for that range | P1 | Active | Tester 3
TC-053 | SPR-080 | Run payroll for the month | Functional | >1 staff users have salary accounts | 1. Finance > Payroll 2. Pick current month 3. Click Run | None | Salary transactions appear for each staff user; running again the same month is prevented or flagged | P2 | Active | Tester 3
TC-054 | SPR-081 | Export full financial report | Functional | Some data exists | 1. Finance > Reports 2. Click Export Full Report 3. Open the downloaded file | None | .xls downloads; opens in Excel showing the expected sheets | P2 | Active | Tester 3
TC-055 | SPR-083 | Non-master cannot reach Finance | Authorization | A non-master admin user exists | 1. Log in as non-master admin 2. Inspect sidebar 3. Manually type /finance/transactions | None | Finance group absent from sidebar; direct URL redirects to /dashboard | P0 | Active | Tester 3
TC-056 | SPR-118 | Email page configured state | Functional | VITE_EMAIL_ENDPOINT + SECRET set in build; GAS bridge deployed and accepting requests | 1. Open SPRConnect > Email 2. Wait for inbox to load | None | Inbox renders within ~5 seconds; refresh icon visible; no "not configured" card | P0 | Active | Tester 3
TC-057 | SPR-119 | Email page not-configured state | Functional | Build with empty VITE_EMAIL_ENDPOINT | 1. Open Email tab | None | "Email isn't configured yet" card renders; no console errors | P0 | Active | Tester 3
TC-058 | SPR-120 | Inbox auto-refresh | Functional | Email bridge configured; recent message exists in Gmail | 1. Open Email 2. Note current top message 3. Send yourself a new email from another account 4. Wait up to 30 seconds without refreshing | External email send | New message appears in the inbox within 30 seconds of arrival in Gmail | P0 | Active | Tester 3
TC-059 | SPR-121 | Send a plain text email | Functional | Email bridge configured; Gmail quota available | 1. Compose 2. To = a Gmail address you control 3. Subject "Test from SPR" 4. Body "Hello" 5. Send 6. Check recipient inbox | Recipient address you can check | Toast "Email sent"; recipient receives message from the configured Gmail account | P0 | Active | Tester 3
TC-060 | SPR-122 | Send email with attachments | Functional | Email bridge configured; <24MB combined attachments | 1. Compose to self 2. Attach a small image + small PDF 3. Send | Two small files | Recipient receives email with both attachments openable | P1 | Active | Tester 3
TC-061 | SPR-123 | Reject sending if mandatory fields missing | Negative | Email bridge configured | 1. Compose with empty To 2. Click Send | Empty To | Error toast; no send attempted | P2 | Active | Tester 3
TC-062 | SPR-125 | Reply pre-fill works | Functional | At least one inbox message exists | 1. Click an inbox row 2. Click Reply 3. Verify pre-filled fields | Use any inbox message | To = sender; Subject prefixed Re: (no double "Re: Re:"); Body has the original snippet quoted | P1 | Active | Tester 3
TC-063 | SPR-126 | Search inbox | Functional | >5 messages in inbox | 1. Open Email 2. Type a sender or keyword in the search box 3. Clear the search | Sample search term | Visible rows narrow to matches; clearing search restores all | P2 | Active | Tester 3
TC-064 | SPR-084 | Start a DM | Functional | Two users exist | 1. Log in as A 2. SPRConnect > Chat 3. Click + 4. Pick user B 5. Send "hi" | Two users | New DM created; message appears for A; for B (after refresh) the same DM and message are present | P0 | Active | Tester 4
TC-065 | SPR-085 | Real-time message arrival | Real-time | Two browsers logged in as A and B; DM open in both | 1. As A send "hello" 2. Observe B's thread without refreshing | Two browsers | B sees message within 3 seconds; unread badge increments if B is on a different page | P0 | Active | Tester 4 | Two-browser test
TC-066 | SPR-086 | Attach an image to chat | Functional | DM is open | 1. Compose message; attach a <2MB image 2. Send | Small image | Image renders inline in both A and B threads; file exists at chats/{chatId}/ in Firebase Storage | P1 | Active | Tester 4
TC-067 | SPR-087 | Attach a PDF to chat | Functional | DM is open | 1. Compose message; attach a small PDF 2. Send | Small PDF | Message shows a file-card with name + size; clicking opens or downloads the PDF | P1 | Active | Tester 4
TC-068 | SPR-088 | Enter sends; Shift+Enter newlines | Functional | DM is open | 1. Type "line1" then press Shift+Enter 2. Type "line2" 3. Press Enter | Multi-line message | Sent message contains a newline between line1 and line2 | P2 | Active | Tester 4
TC-069 | SPR-089 | Per-chat unread badge | Functional | Two browsers as A and B | 1. B navigates away from chat 2. A sends 3 messages 3. B returns to chat list | None | Chat row shows badge "3"; opening the chat clears the badge | P1 | Active | Tester 4
TC-070 | SPR-091 | Announcements admin posts; non-admin sees read-only | Authorization | One admin and one non-admin user exist | 1. As admin open Chat > Announcements; verify composer present; post a message 2. As non-admin open Announcements | Two users | Admin composer visible and works; non-admin sees the message but sees "Read-only" instead of composer | P1 | Active | Tester 4
TC-071 | SPR-096 | Schedule a meeting | Functional | Two users exist | 1. SPRConnect > Meetings > New 2. Title "Sync"; start tomorrow 10:00; end 10:30; participant user B 3. Save | Provided | Meeting appears under Tomorrow with my RSVP=Going; B (on refresh) sees the meeting with RSVP=Pending | P0 | Active | Tester 4
TC-072 | SPR-097 | RSVP propagates live | Real-time | Two browsers; meeting B is invited to | 1. As B open the meeting and click Going 2. As A (organizer) watch participant badges | None | A sees B's badge change to Going within 3 seconds without refresh | P0 | Active | Tester 4
TC-073 | SPR-100 | Edit a meeting | Functional | A meeting I organize exists | 1. Open meeting 2. Change time and add a new participant 3. Save | New time + participant | Changes persist; new participant sees the meeting with RSVP=Pending; existing RSVPs preserved | P1 | Active | Tester 4
TC-074 | SPR-101 | Cancel a meeting | Functional | A scheduled meeting I organize exists | 1. Open meeting 2. Click Cancel and confirm | None | Status=Cancelled; Cancelled badge shows; Join button disappears | P1 | Active | Tester 4
TC-075 | SPR-102 | Only organizer can edit/cancel | Authorization | A meeting organized by user A exists; user B is a participant | 1. Log in as B 2. Open the meeting 3. Look for Edit / Cancel buttons | B is not organizer | No Edit or Cancel buttons; B can only RSVP | P1 | Active | Tester 4
TC-076 | SPR-103 | Sidebar Today badge | Functional | A meeting scheduled for today exists | 1. Refresh 2. Inspect sidebar SPRConnect > Meetings | None | Badge "Today: N" displays correctly with N reflecting today's meeting count | P2 | Active | Tester 4
TC-077 | SPR-106 | Schedule from DM pre-selects participant | Functional | A DM with user B is open | 1. In the chat header, click Schedule 2. Verify the meeting modal | None | Modal opens with B pre-checked as a participant; organizer is me by default | P2 | Active | Tester 4
TC-078 | SPR-107 | Validate end time after start time | Negative | New meeting form | 1. Open New Meeting 2. Set end time <= start time 3. Click Save | Invalid end time | Inline error; save blocked | P2 | Active | Tester 4
TC-079 | SPR-108 | Start a call from DM | Functional | A DM with B is open | 1. Click Call in the chat header 2. Verify navigation 3. Check Firestore /callInvitations | None | Navigated to /call/<roomId>; CallInvitation row exists with status=ringing and caller=me | P0 | Active | Tester 4
TC-080 | SPR-109 | Ring overlay regardless of page | Real-time | Two browsers; B is on /candidates when A calls | 1. As A call B 2. Observe B's screen | Two browsers | B sees ring overlay within 3 seconds with A's name; Accept/Decline buttons visible; ringtone plays (browser audio permission required) | P0 | Active | Tester 4 | Two-browser test
TC-081 | SPR-110 | Accept call joins the same Jitsi room | Functional | A is on /call ringing B | 1. As B click Accept 2. Both screens now show Jitsi 3. A signs into Google when prompted | Google account for moderator | Both see each other's video and hear audio; invitation status=accepted | P0 | Active | Tester 4 | meet.jit.si requires one-time Google sign-in for the moderator
TC-082 | SPR-111 | Decline call notifies caller | Real-time | A is on /call ringing B | 1. As B click Decline 2. Observe A's screen | None | Ring overlay closes on B; A sees toast "B declined the call" and is taken back to /chat; invitation status=declined | P1 | Active | Tester 4
TC-083 | SPR-112 | Ring overlay TTL | Functional | Two browsers; A calls B; B does nothing | 1. Start the call from A 2. Leave B on the ringing screen without action 3. Wait 45 seconds | None | Overlay auto-hides on B after ~45 seconds | P2 | Active | Tester 4
TC-084 | SPR-113 | Join scheduled-meeting call | Functional | A scheduled meeting I am invited to exists | 1. Open the meeting card 2. Click Join 3. Verify the call page | None | /call opens with the meeting title preset; Jitsi room is shared across all invitees who click Join | P0 | Active | Tester 4
TC-085 | SPR-114 | Leave call returns to source | Functional | I am in a call started from /chat | 1. Click Leave | None | Return to /chat; if I was the caller, invitation is marked status=ended | P1 | Active | Tester 4
TC-086 | SPR-130 | Full smoke on Chrome | Smoke | Latest QA build deployed | 1. Open QA URL in Chrome 2. Run the smoke checklist (login → dashboard → candidates → chat → meeting → email) 3. Inspect console | Chrome latest | All checks pass; no console errors | P0 | Active | Tester 1 | Repeat every sprint
TC-087 | SPR-131 | Full smoke on Edge | Smoke | Latest QA build deployed | 1. Same checklist on Edge | Edge latest | All checks pass | P0 | Active | Tester 1
TC-088 | SPR-133 | Real-time sync across two browsers | Real-time | Two browsers as A and B | 1. As A add a candidate 2. As B (on /candidates) watch the list | Two browsers | B sees the new candidate within 5 seconds without refresh | P0 | Active | Tester 1
TC-089 | SPR-128 | Tablet layout (1024px) | Responsive | QA build | 1. DevTools set viewport 1024×768 2. Visit dashboard, candidates, chat, meetings 3. Inspect overflow | Browser DevTools | No horizontal scroll; sidebar collapses cleanly; all pages remain usable | P2 | Active | Tester 1
TC-090 | SPR-129 | Phone layout (375px) | Responsive | QA build | 1. DevTools 375×812 2. Visit dashboard, candidates, chat 3. Open the mobile menu | Browser DevTools | Mobile menu replaces sidebar; content readable; no horizontal scroll | P2 | Active | Tester 1
TC-091 | SPR-137 | QA data does not leak into prod | Authorization | Logged into QA; Firebase Console open in another tab | 1. On QA, add a unique-named candidate 2. In Firebase Console, check sprtechforge-qa Firestore 3. Switch to sprtechforge (prod) project and verify | Unique name like "QA-Test-Candidate-2026-05-17" | Candidate exists in sprtechforge-qa only; sprtechforge prod has no such record | P0 | Active | Tester 1

## Bugs
Bug ID | Title | Module / Epic | Story ID | Test Case ID | Severity | Priority | Status | Reporter | Date Reported | Assignee | Environment | Browser & OS | Build / Commit | Pre-conditions | Steps to Reproduce | Expected Result | Actual Result | Frequency | Workaround | Screenshot Link | Loom / Video Link | Date Resolved | Fixed In Build | Verified By | Sprint | Comments
BUG-001 | Cancelling an interview does not clear the today badge | E5 Interviews | SPR-061 | TC-041 | High | P1 | New | Tester 2 | 2026-05-18 |  | QA | Chrome 127 / Win 11 | <commit> | Logged in as admin; at least one scheduled interview today | 1. Schedule interview for today 2. Open Interviews list 3. Cancel it 4. Look at sidebar badge | Sidebar "Today: N" badge decrements by 1 | Badge shows the old count; only updates after a full page refresh | Always | Refresh the page | /shared/bugs/BUG-001.png |  |  |  |  | S2 | Example row — replace with real bugs as you find them.
BUG-002 | Bootstrap admin write triggered on every login | E1 Auth & Users | SPR-011 | TC-010 | Low | P3 | New | Tester 1 | 2026-05-18 |  | QA | Edge 127 / Win 11 | <commit> | Logged in as bootstrap admin | 1. Login as admin-01 2. Inspect Firebase Console > Firestore > users history | A single write only when admin-01 is missing | Write happens on every login even when admin-01 already exists | Always | None needed | [5 empty] | S2 | Example row — probably a harmless no-op write but inflates Firestore writes.

## Test Execution
Cycle | Sprint | TC ID | Story ID | Title | Executed By | Execution Date | Browser & OS | Build / Commit | Status | Actual Result | Bugs Raised | Time Taken (min) | Notes
S1-Cycle1 | S1 | TC-001 | SPR-001 | Login with valid bootstrap admin | Tester 1 | 2026-05-18 | Chrome 127 / Win 11 | <commit> | Pass | Login worked; dashboard loaded; SESSION_KEY present |  | 2
S1-Cycle1 | S1 | TC-002 | SPR-002 | Login with wrong password | Tester 1 | 2026-05-18 | Chrome 127 / Win 11 | <commit> | Pass | Inline error shown as expected |  | 1

## Sprint Board
Sprint | Weeks | Story ID | Title | Epic | Owner | Priority | Effort | Status | Committed | Done | Notes
S0 | Week 1 | S0-01 | Create QA accounts for all 4 testers | Cross-cutting | Lead | P0 | 2 | Sprint | Yes |  | Setup; not a user story
S0 | Week 1 | S0-02 | Set up SPR-Testing.xlsx in shared drive (OneDrive / SharePoint / Google Drive) | Cross-cutting | Lead | P0 | 2 | Sprint | Yes |  | Setup; not a user story
S0 | Week 1 | S0-03 | Bootstrap admin password rotated and shared securely | Cross-cutting | Lead | P0 | 2 | Sprint | Yes |  | Setup; not a user story
S0 | Week 1 | S0-04 | Playwright scaffold + initial smoke suite committed | Cross-cutting | Lead | P0 | 2 | Sprint | Yes |  | Setup; not a user story
S0 | Week 1 | S0-05 | GitHub Actions e2e workflow green on DevelopmentBranch | Cross-cutting | Lead | P0 | 2 | Sprint | Yes |  | Setup; not a user story
S0 | Week 1 | S0-06 | Daily bug-triage time on every tester's calendar | Cross-cutting | Lead | P0 | 2 | Sprint | Yes |  | Setup; not a user story
S1 | Weeks 2–3 | SPR-001 | Login with valid credentials | E1 Auth & Users | Tester 1 | P0 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-002 | Login with wrong password shows error | E1 Auth & Users | Tester 1 | P0 | 1 | Sprint | Yes
S1 | Weeks 2–3 | SPR-003 | Login with unknown username shows error | E1 Auth & Users | Tester 1 | P0 | 1 | Sprint | Yes
S1 | Weeks 2–3 | SPR-004 | Login form rejects empty fields | E1 Auth & Users | Tester 1 | P1 | 1 | Sprint | Yes
S1 | Weeks 2–3 | SPR-005 | Username is case-insensitive | E1 Auth & Users | Tester 1 | P1 | 1 | Sprint | Yes
S1 | Weeks 2–3 | SPR-006 | Login attempt is recorded in activity log | E1 Auth & Users | Tester 1 | P2 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-007 | Logout returns to landing page | E1 Auth & Users | Tester 1 | P1 | 1 | Sprint | Yes
S1 | Weeks 2–3 | SPR-008 | Session persists across browser refresh | E1 Auth & Users | Tester 1 | P1 | 1 | Sprint | Yes
S1 | Weeks 2–3 | SPR-009 | Session expires after 60 minutes idle | E1 Auth & Users | Tester 1 | P1 | 2 | Sprint | Yes |  | Clock manipulation via localStorage
S1 | Weeks 2–3 | SPR-010 | Bootstrap admin can log in on empty users collection | E1 Auth & Users | Tester 1 | P0 | 1 | Sprint | Yes
S1 | Weeks 2–3 | SPR-011 | Bootstrap admin auto-persists when users collection is first populated | E1 Auth & Users | Tester 1 | P0 | 1 | Sprint | Yes |  | Past prod incident — must remain green forever
S1 | Weeks 2–3 | SPR-012 | User can submit a password reset request | E1 Auth & Users | Tester 1 | P2 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-013 | Master can resolve a password reset request | E1 Auth & Users | Tester 1 | P2 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-014 | Admin adds a new user | E1 Auth & Users | Tester 1 | P0 | 3 | Sprint | Yes
S1 | Weeks 2–3 | SPR-015 | Adding a user with a duplicate username is rejected | E1 Auth & Users | Tester 1 | P1 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-016 | Admin edits a user | E1 Auth & Users | Tester 1 | P1 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-017 | Admin can change a user's password | E1 Auth & Users | Tester 1 | P2 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-018 | Admin deletes a user | E1 Auth & Users | Tester 1 | P2 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-019 | Admin assigns modules to a user | E1 Auth & Users | Tester 1 | P1 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-020 | Master role grants Finance access regardless of modules | E1 Auth & Users | Tester 1 | P0 | 1 | Sprint | Yes
S1 | Weeks 2–3 | SPR-021 | Master views the activity log | E1 Auth & Users | Tester 1 | P1 | 2 | Sprint | Yes
S1 | Weeks 2–3 | SPR-022 | Master can clear activity logs | E1 Auth & Users | Tester 1 | P2 | 2 | Sprint | Yes
S2 | Weeks 4–5 | SPR-023 | Add a new candidate with required fields | E2 Candidates | Tester 2 | P0 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-024 | Add candidate with invalid email is rejected | E2 Candidates | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-025 | Edit candidate name | E2 Candidates | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-026 | Edit candidate contact details | E2 Candidates | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-027 | Edit candidate batch / status | E2 Candidates | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-028 | Delete candidate with no dependencies | E2 Candidates | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-029 | Delete candidate with linked records — behaviour confirmed | E2 Candidates | Tester 2 | P2 | 3 | Backlog | No |  | Verify current behaviour and document it
S2 | Weeks 4–5 | SPR-030 | Search candidates by name | E2 Candidates | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-031 | Filter candidates by status | E2 Candidates | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-032 | Pagination on candidate list | E2 Candidates | Tester 2 | P3 | 2 | Backlog | No |  | If pagination is implemented; otherwise mark Won't Fix
S2 | Weeks 4–5 | SPR-033 | View candidate detail page | E2 Candidates | Tester 2 | P1 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-034 | Complete candidate profile | E2 Candidates | Tester 2 | P1 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-035 | Upload candidate resume | E2 Candidates | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-036 | Send agreement to candidate | E2 Candidates | Tester 2 | P1 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-037 | Candidate accepts agreement via portal | E2 Candidates | Tester 2 | P1 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-038 | Candidate rejects agreement with reason | E2 Candidates | Tester 2 | P2 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-039 | Mark candidate as Placed with package details | E2 Candidates | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-040 | Work Support tracking | E2 Candidates | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-041 | Add a new enquiry | E3 Enquiries & Leads | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-042 | Add a note to an enquiry | E3 Enquiries & Leads | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-043 | Update enquiry status | E3 Enquiries & Leads | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-044 | Merge a Joined enquiry into a new candidate | E3 Enquiries & Leads | Tester 2 | P1 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-045 | Search enquiries | E3 Enquiries & Leads | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-046 | View web leads | E3 Enquiries & Leads | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-047 | Mark a web lead as read | E3 Enquiries & Leads | Tester 2 | P2 | 1 | Backlog | No
S2 | Weeks 4–5 | SPR-048 | Update web lead status | E3 Enquiries & Leads | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-049 | Create a training module | E4 Training | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-050 | Edit / reorder modules | E4 Training | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-051 | Add a topic under a module | E4 Training | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-052 | Record daily attendance | E4 Training | Tester 2 | P0 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-053 | Record assignment status alongside attendance | E4 Training | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-054 | Track candidate progress (admin) | E4 Training | Tester 2 | P2 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-055 | Candidate views their own training dashboard | E4 Training | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-056 | View Curriculum (read-only) for candidates | E4 Training | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-057 | Schedule an interview | E5 Interviews | Tester 2 | P0 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-058 | Edit an interview | E5 Interviews | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-059 | Mark interview outcome | E5 Interviews | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-060 | Reschedule an interview | E5 Interviews | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-061 | Cancel an interview | E5 Interviews | Tester 2 | P1 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-062 | Sidebar shows "Today: N" badge for interviews | E5 Interviews | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-063 | Manage interview question bank | E5 Interviews | Tester 2 | P2 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-064 | Candidate runs an interview prep session | E5 Interviews | Tester 2 | P2 | 3 | Backlog | No
S2 | Weeks 4–5 | SPR-065 | View interview prep history (admin) | E5 Interviews | Tester 2 | P3 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-138 | Address book lists candidates with contact details | E2 Candidates | Tester 2 | P2 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-139 | Address book search and copy | E2 Candidates | Tester 2 | P3 | 2 | Backlog | No
S2 | Weeks 4–5 | SPR-140 | Candidate notes are persisted | E2 Candidates | Tester 2 | P2 | 1 | Backlog | No
S3 | Weeks 6–7 | SPR-066 | Add a Bank account | E6 Finance | Tester 3 | P0 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-067 | Add a Candidate / Debtor account | E6 Finance | Tester 3 | P1 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-068 | Edit an account | E6 Finance | Tester 3 | P1 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-069 | Delete an account | E6 Finance | Tester 3 | P2 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-070 | Record an Income transaction | E6 Finance | Tester 3 | P0 | 3 | Backlog | No
S3 | Weeks 6–7 | SPR-071 | Record a Payment transaction | E6 Finance | Tester 3 | P0 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-072 | Record a Transfer between accounts | E6 Finance | Tester 3 | P1 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-073 | Record a Refund transaction | E6 Finance | Tester 3 | P2 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-074 | Lock a transaction | E6 Finance | Tester 3 | P1 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-075 | Edit an unlocked transaction | E6 Finance | Tester 3 | P1 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-076 | Delete an unlocked transaction | E6 Finance | Tester 3 | P1 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-077 | View account statement | E6 Finance | Tester 3 | P1 | 3 | Backlog | No
S3 | Weeks 6–7 | SPR-078 | Generate Balance Sheet | E6 Finance | Tester 3 | P1 | 3 | Backlog | No
S3 | Weeks 6–7 | SPR-079 | Generate Profit & Loss | E6 Finance | Tester 3 | P1 | 3 | Backlog | No
S3 | Weeks 6–7 | SPR-080 | Run payroll for a month | E6 Finance | Tester 3 | P2 | 3 | Backlog | No
S3 | Weeks 6–7 | SPR-081 | Export full financial report | E6 Finance | Tester 3 | P2 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-082 | Finance Dashboard reconciles with detail pages | E6 Finance | Tester 3 | P2 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-083 | Non-master cannot access Finance routes | E6 Finance | Tester 3 | P0 | 1 | Backlog | No
S3 | Weeks 6–7 | SPR-118 | Email page shows configured state | E10 Email | Tester 3 | P0 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-119 | Email page shows not-configured fallback | E10 Email | Tester 3 | P0 | 1 | Backlog | No
S3 | Weeks 6–7 | SPR-120 | Inbox loads and auto-refreshes | E10 Email | Tester 3 | P0 | 3 | Backlog | No
S3 | Weeks 6–7 | SPR-121 | Send a plain text email | E10 Email | Tester 3 | P0 | 3 | Backlog | No
S3 | Weeks 6–7 | SPR-122 | Send email with multiple attachments | E10 Email | Tester 3 | P1 | 3 | Backlog | No
S3 | Weeks 6–7 | SPR-123 | Reject sending if To/Subject/Body missing | E10 Email | Tester 3 | P2 | 1 | Backlog | No
S3 | Weeks 6–7 | SPR-124 | Send to multiple recipients (comma-separated) | E10 Email | Tester 3 | P2 | 1 | Backlog | No
S3 | Weeks 6–7 | SPR-125 | Reply to an inbox message | E10 Email | Tester 3 | P1 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-126 | Search the inbox | E10 Email | Tester 3 | P2 | 2 | Backlog | No
S3 | Weeks 6–7 | SPR-127 | Bad shared secret returns error | E10 Email | Tester 3 | P2 | 1 | Backlog | No
S3 | Weeks 6–7 | SPR-141 | Master can change Firebase config via Cloud Setup | E1 Auth & Users | Tester 3 | P3 | 3 | Backlog | No
S3 | Weeks 6–7 | SPR-142 | Master can run the in-app Test Runner | E1 Auth & Users | Tester 3 | P3 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-084 | Start a DM with another user | E7 Chat | Tester 4 | P0 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-085 | Send a text message in a DM | E7 Chat | Tester 4 | P0 | 3 | Backlog | No |  | Two-browser test
S4 | Weeks 8–9 | SPR-086 | Send a chat message with an image attachment | E7 Chat | Tester 4 | P1 | 3 | Backlog | No
S4 | Weeks 8–9 | SPR-087 | Send a chat message with a non-image attachment | E7 Chat | Tester 4 | P1 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-088 | Composer keyboard shortcuts | E7 Chat | Tester 4 | P2 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-089 | Unread badge per chat | E7 Chat | Tester 4 | P1 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-090 | Sidebar Chat unread badge | E7 Chat | Tester 4 | P1 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-091 | Admin posts in Announcements channel | E7 Chat | Tester 4 | P1 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-092 | Announcements channel auto-creates on first open | E7 Chat | Tester 4 | P2 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-093 | Chat list sorts by lastMessageAt | E7 Chat | Tester 4 | P2 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-094 | Message ordering is stable | E7 Chat | Tester 4 | P2 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-095 | Search users in New DM modal | E7 Chat | Tester 4 | P2 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-096 | Schedule a new meeting | E8 Meetings | Tester 4 | P0 | 3 | Backlog | No
S4 | Weeks 8–9 | SPR-097 | Participant RSVPs Going | E8 Meetings | Tester 4 | P0 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-098 | Participant RSVPs Maybe | E8 Meetings | Tester 4 | P1 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-099 | Participant declines | E8 Meetings | Tester 4 | P1 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-100 | Edit a meeting | E8 Meetings | Tester 4 | P1 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-101 | Cancel a meeting | E8 Meetings | Tester 4 | P1 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-102 | Permission to edit / cancel is enforced | E8 Meetings | Tester 4 | P1 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-103 | Today's meetings badge in sidebar | E8 Meetings | Tester 4 | P2 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-104 | Tabs filter meetings | E8 Meetings | Tester 4 | P2 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-105 | Meeting card grouping by date | E8 Meetings | Tester 4 | P2 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-106 | Schedule a meeting from a chat DM | E8 Meetings | Tester 4 | P2 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-107 | Validation: end time must be after start time | E8 Meetings | Tester 4 | P2 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-108 | Start a video call from a DM | E9 Video Calls | Tester 4 | P0 | 3 | Backlog | No
S4 | Weeks 8–9 | SPR-109 | Callee sees the ring overlay regardless of page | E9 Video Calls | Tester 4 | P0 | 3 | Backlog | No |  | Two-browser test
S4 | Weeks 8–9 | SPR-110 | Callee accepts the call | E9 Video Calls | Tester 4 | P0 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-111 | Callee declines the call | E9 Video Calls | Tester 4 | P1 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-112 | Ring overlay auto-hides after 45s (TTL) | E9 Video Calls | Tester 4 | P2 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-113 | Join a scheduled meeting via video | E9 Video Calls | Tester 4 | P0 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-114 | Leave call returns to source page | E9 Video Calls | Tester 4 | P1 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-115 | Jitsi readyToClose event also triggers leave | E9 Video Calls | Tester 4 | P2 | 2 | Backlog | No
S4 | Weeks 8–9 | SPR-116 | Cannot call yourself | E9 Video Calls | Tester 4 | P3 | 1 | Backlog | No
S4 | Weeks 8–9 | SPR-117 | Ringing overlay does not appear when in a call | E9 Video Calls | Tester 4 | P2 | 2 | Backlog | No
S5 | Week 10 | SPR-128 | Tablet layout (1024px) | Cross-cutting | Tester 1 | P2 | 3 | Backlog | No
S5 | Week 10 | SPR-129 | Phone layout (375px) | Cross-cutting | Tester 1 | P2 | 3 | Backlog | No
S5 | Week 10 | SPR-130 | Smoke pass on Chrome (Tier 1) | Cross-cutting | Tester 1 | P0 | 2 | Backlog | No
S5 | Week 10 | SPR-131 | Smoke pass on Edge (Tier 1) | Cross-cutting | Tester 1 | P0 | 2 | Backlog | No
S5 | Week 10 | SPR-132 | Smoke pass on Firefox (Tier 2) | Cross-cutting | Tester 1 | P1 | 2 | Backlog | No
S5 | Week 10 | SPR-133 | Real-time sync across two browsers | Cross-cutting | Tester 1 | P0 | 2 | Backlog | No
S5 | Week 10 | SPR-134 | No JS errors in production console | Cross-cutting | Tester 1 | P1 | 2 | Backlog | No
S5 | Week 10 | SPR-135 | Activity log entries are accurate and complete | Cross-cutting | Tester 1 | P1 | 3 | Backlog | No
S5 | Week 10 | SPR-136 | Keyboard navigation through key forms | Cross-cutting | Tester 1 | P2 | 2 | Backlog | No
S5 | Week 10 | SPR-137 | No data leak between QA and production | Cross-cutting | Tester 1 | P0 | 1 | Backlog | No
S5 | Week 10 | S5-X1 | Full regression run across all P0/P1 stories | Cross-cutting | Lead | P0 | 5 | Backlog | No
S5 | Week 10 | S5-X2 | Release Test Report (sign-off doc) | Cross-cutting | Lead | P0 | 2 | Backlog | No
S5 | Week 10 | S5-X3 | UAT with project owner (master role) | Cross-cutting | Owner | P0 | 3 | Backlog | No

## Automation Coverage
TC ID | Story ID | Title | Priority | Automation Status | Spec File | Last Run | Last Run Result | Flakiness (%) | Automation Owner | Notes
TC-001 | SPR-001 | Login with valid bootstrap admin | P0 | Planned |  |  |  |  | Tester 1
TC-002 | SPR-002 | Login with wrong password | P0 | Planned |  |  |  |  | Tester 1
TC-003 | SPR-003 | Login with unknown username | P0 | Planned |  |  |  |  | Tester 1
TC-004 | SPR-004 | Login with empty fields | P1 | Planned |  |  |  |  | Tester 1
TC-005 | SPR-005 | Username login is case-insensitive | P1 | Planned |  |  |  |  | Tester 1
TC-006 | SPR-007 | Logout returns to landing | P1 | Planned |  |  |  |  | Tester 1
TC-007 | SPR-008 | Session persists across refresh | P1 | Planned |  |  |  |  | Tester 1
TC-008 | SPR-009 | Session expires after 60 min idle | P1 | Planned |  |  |  |  | Tester 1
TC-009 | SPR-010 | Bootstrap admin login on empty users collection | P0 | Planned |  |  |  |  | Tester 1
TC-010 | SPR-011 | Bootstrap admin auto-persists regression | P0 | Planned |  |  |  |  | Tester 1
TC-011 | SPR-014 | Admin adds a new user | P0 | Planned |  |  |  |  | Tester 1
TC-012 | SPR-015 | Duplicate username rejected | P1 | Planned |  |  |  |  | Tester 1
TC-013 | SPR-016 | Admin edits user; rename reflects in chat | P1 | Planned |  |  |  |  | Tester 1
TC-014 | SPR-018 | Admin deletes a user | P2 | Planned |  |  |  |  | Tester 1
TC-015 | SPR-019 | Module assignment controls sidebar | P1 | Planned |  |  |  |  | Tester 1
TC-016 | SPR-020 | Master vs non-master Finance access | P0 | Planned |  |  |  |  | Tester 1
TC-017 | SPR-021 | Master views activity log | P1 | Planned |  |  |  |  | Tester 1
TC-018 | SPR-023 | Add a new candidate | P0 | Planned |  |  |  |  | Tester 1
TC-019 | SPR-024 | Add candidate with invalid email | P2 | Planned |  |  |  |  | Tester 1
TC-020 | SPR-025 | Edit candidate name | P1 | Planned |  |  |  |  | Tester 1
TC-021 | SPR-027 | Change candidate status to Placed | P1 | Planned |  |  |  |  | Tester 1
TC-022 | SPR-030 | Search candidates by name | P2 | Planned |  |  |  |  | Tester 1
TC-023 | SPR-035 | Upload and download resume | P2 | Planned |  |  |  |  | Tester 1
TC-024 | SPR-036 | Send agreement to candidate | P1 | Planned |  |  |  |  | Tester 1
TC-025 | SPR-037 | Candidate accepts agreement via portal | P1 | Planned |  |  |  |  | Tester 1
TC-026 | SPR-038 | Candidate rejects agreement | P2 | Planned |  |  |  |  | Tester 1
TC-027 | SPR-041 | Add a new enquiry | P1 | Planned |  |  |  |  | Tester 1
TC-028 | SPR-042 | Add note to enquiry | P2 | Planned |  |  |  |  | Tester 1
TC-029 | SPR-043 | Move enquiry through statuses | P1 | Planned |  |  |  |  | Tester 1
TC-030 | SPR-044 | Merge enquiry into candidate | P1 | Planned |  |  |  |  | Tester 1
TC-031 | SPR-046 | View web leads with unread badge | P2 | Planned |  |  |  |  | Tester 1
TC-032 | SPR-047 | Mark a web lead as read | P2 | Planned |  |  |  |  | Tester 1
TC-033 | SPR-049 | Create a training module | P1 | Planned |  |  |  |  | Tester 1
TC-034 | SPR-051 | Add a topic under a module | P1 | Planned |  |  |  |  | Tester 1
TC-035 | SPR-052 | Record daily attendance | P0 | Planned |  |  |  |  | Tester 1
TC-036 | SPR-053 | Record assignment status alongside attendance | P1 | Planned |  |  |  |  | Tester 1
TC-037 | SPR-054 | Progress tracker aggregates correctly | P2 | Planned |  |  |  |  | Tester 1
TC-038 | SPR-055 | Candidate sees only their own training | P1 | Planned |  |  |  |  | Tester 1
TC-039 | SPR-057 | Schedule an interview | P0 | Planned |  |  |  |  | Tester 1
TC-040 | SPR-058 | Reschedule an interview | P1 | Planned |  |  |  |  | Tester 1
TC-041 | SPR-061 | Cancel an interview | P1 | Planned |  |  |  |  | Tester 1
TC-042 | SPR-063 | Manage interview question bank | P2 | Planned |  |  |  |  | Tester 1
TC-043 | SPR-066 | Add a Bank account | P0 | Planned |  |  |  |  | Tester 1
TC-044 | SPR-070 | Record income transaction | P0 | Planned |  |  |  |  | Tester 1
TC-045 | SPR-071 | Record payment transaction | P0 | Planned |  |  |  |  | Tester 1
TC-046 | SPR-072 | Transfer between bank accounts | P1 | Planned |  |  |  |  | Tester 1
TC-047 | SPR-074 | Lock a transaction prevents edits | P1 | Planned |  |  |  |  | Tester 1
TC-048 | SPR-075 | Edit an unlocked transaction | P1 | Planned |  |  |  |  | Tester 1
TC-049 | SPR-076 | Delete an unlocked transaction | P1 | Planned |  |  |  |  | Tester 1
TC-050 | SPR-077 | View account statement | P1 | Planned |  |  |  |  | Tester 1
TC-051 | SPR-078 | Balance sheet reconciles | P1 | Planned |  |  |  |  | Tester 1
TC-052 | SPR-079 | P&L reconciles by date range | P1 | Planned |  |  |  |  | Tester 1
TC-053 | SPR-080 | Run payroll for the month | P2 | Planned |  |  |  |  | Tester 1
TC-054 | SPR-081 | Export full financial report | P2 | Planned |  |  |  |  | Tester 1
TC-055 | SPR-083 | Non-master cannot reach Finance | P0 | Planned |  |  |  |  | Tester 1
TC-056 | SPR-118 | Email page configured state | P0 | Planned |  |  |  |  | Tester 1
TC-057 | SPR-119 | Email page not-configured state | P0 | Planned |  |  |  |  | Tester 1
TC-058 | SPR-120 | Inbox auto-refresh | P0 | Planned |  |  |  |  | Tester 1
TC-059 | SPR-121 | Send a plain text email | P0 | Planned |  |  |  |  | Tester 1
TC-060 | SPR-122 | Send email with attachments | P1 | Planned |  |  |  |  | Tester 1
TC-061 | SPR-123 | Reject sending if mandatory fields missing | P2 | Planned |  |  |  |  | Tester 1
TC-062 | SPR-125 | Reply pre-fill works | P1 | Planned |  |  |  |  | Tester 1
TC-063 | SPR-126 | Search inbox | P2 | Planned |  |  |  |  | Tester 1
TC-064 | SPR-084 | Start a DM | P0 | Planned |  |  |  |  | Tester 1
TC-065 | SPR-085 | Real-time message arrival | P0 | Manual |  |  |  |  | Tester 1
TC-066 | SPR-086 | Attach an image to chat | P1 | Planned |  |  |  |  | Tester 1
TC-067 | SPR-087 | Attach a PDF to chat | P1 | Planned |  |  |  |  | Tester 1
TC-068 | SPR-088 | Enter sends; Shift+Enter newlines | P2 | Planned |  |  |  |  | Tester 1
TC-069 | SPR-089 | Per-chat unread badge | P1 | Planned |  |  |  |  | Tester 1
TC-070 | SPR-091 | Announcements admin posts; non-admin sees read-only | P1 | Planned |  |  |  |  | Tester 1
TC-071 | SPR-096 | Schedule a meeting | P0 | Planned |  |  |  |  | Tester 1
TC-072 | SPR-097 | RSVP propagates live | P0 | Manual |  |  |  |  | Tester 1
TC-073 | SPR-100 | Edit a meeting | P1 | Planned |  |  |  |  | Tester 1
TC-074 | SPR-101 | Cancel a meeting | P1 | Planned |  |  |  |  | Tester 1
TC-075 | SPR-102 | Only organizer can edit/cancel | P1 | Planned |  |  |  |  | Tester 1
TC-076 | SPR-103 | Sidebar Today badge | P2 | Planned |  |  |  |  | Tester 1
TC-077 | SPR-106 | Schedule from DM pre-selects participant | P2 | Planned |  |  |  |  | Tester 1
TC-078 | SPR-107 | Validate end time after start time | P2 | Planned |  |  |  |  | Tester 1
TC-079 | SPR-108 | Start a call from DM | P0 | Planned |  |  |  |  | Tester 1
TC-080 | SPR-109 | Ring overlay regardless of page | P0 | Manual |  |  |  |  | Tester 1
TC-081 | SPR-110 | Accept call joins the same Jitsi room | P0 | Planned |  |  |  |  | Tester 1
TC-082 | SPR-111 | Decline call notifies caller | P1 | Manual |  |  |  |  | Tester 1
TC-083 | SPR-112 | Ring overlay TTL | P2 | Planned |  |  |  |  | Tester 1
TC-084 | SPR-113 | Join scheduled-meeting call | P0 | Planned |  |  |  |  | Tester 1
TC-085 | SPR-114 | Leave call returns to source | P1 | Planned |  |  |  |  | Tester 1
TC-086 | SPR-130 | Full smoke on Chrome | P0 | Automated | tests/e2e/tc-086.spec.ts |  |  |  | Tester 1
TC-087 | SPR-131 | Full smoke on Edge | P0 | Automated | tests/e2e/tc-087.spec.ts |  |  |  | Tester 1
TC-088 | SPR-133 | Real-time sync across two browsers | P0 | Manual |  |  |  |  | Tester 1
TC-089 | SPR-128 | Tablet layout (1024px) | P2 | Manual |  |  |  |  | Tester 1
TC-090 | SPR-129 | Phone layout (375px) | P2 | Manual |  |  |  |  | Tester 1
TC-091 | SPR-137 | QA data does not leak into prod | P0 | Planned |  |  |  |  | Tester 1